## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Chowlpur and Its Adjoining mouzas water Supply Scheme for providing Functional House Tap Connection under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08728 | Retrofitting | Providing Functional School, Anganwadi and Health Center Tap Connection and allied works of Command area at Chowlpur & others Ground Water Supply Scheme under Barasat-II Block Under '' JAL SWAPNA'' programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000192/2021-2022 | 364/B.Ar.D | 03/03/2022 | 18/03/2022 | SANTU GHOSH | 3.91 | 3.9 | 99.59 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Chowlpur and Its Adjoining mouzas water Supply Scheme for providing Functional House Tap Connection under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08728 | Retrofitting | Providing Functional Household Tap Connection (FHTC) and allied works Malrameswarpur, Kharigacchi, Chaturbhujpur and Kalikapur mouza of Barasat-II Block from Chowlpur & Its Adjoining Mouzas Ground Water Supply Scheme Under "JAL SWAPNA" programme under Barasat Arsenic Division, PHE Dte. Phase-II | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000124/2021-2022 | 2077/B.Ar.D. | 02/12/2021 | 02/03/2022 | BANERJEE CONSTRUCTION | 99.13 | 98.52 | 99.38 | 100
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Chowlpur and Its Adjoining mouzas water Supply Scheme for providing Functional House Tap Connection under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08728 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling (approx. 48 mtr length) for protection of different dia UPVC/HDPE Pipeline near pond of Sardarhati opposite Sardarhati Hari Mandir under Chowlpur W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000178/2021-2022 | 265/B.Ar.D | 18/02/2022 | 10/03/2022 | M/S DAS & CO | 4.71 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Chowlpur and Its Adjoining mouzas water Supply Scheme for providing Functional House Tap Connection under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08728 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling (approx. 50 mtr length) for protection of different dia UPVC/HDPE Pipeline near two ponds at Ghoradaria opposite Ranjit Mandal house and at Malrameswarpur Sardarhati opposite Pradip Sarkar house under Chowlpur W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000289/2021-2022 | 563/B.Ar.D | 23/03/2022 | 07/04/2022 | NANDY UDYOG | 4.66 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Chowlpur and Its Adjoining mouzas water Supply Scheme for providing Functional House Tap Connection under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08728 | Retrofitting | Road restoration due to laying of various dia UPVC/HDPE Pipe distribution line at Kalikapur of Chowlpur W/S Scheme under Barasat -II block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000177/2022-2023 | 36/B.Ar.D | 05/01/2023 | 26/01/2023 | P. & S. ASSOCIATES | 0.95 | 0.93 | 97.54 | 1
Total | [13 empty] | 113.36 | 103.35 | 91.16