## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Chaumuha Water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08729 | Retrofitting | Route survey, distribution design & DPR preparation for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Chowmuha & its adjoining mouza water supply scheme in Barasat -II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000062/2021-2022 | 1699/B.Ar.D | 30/09/2021 | 15/10/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.38 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Chaumuha Water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08729 | Retrofitting | Providing Functional House Hod Connection and Allied workas at Dhokra and Khamar Nowabad Mouzas of Barasat II Block from Chaumuha & Its Adjoining Mouzas Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000073/2021-2022 | 1724/B.Ar.D. | 01/10/2021 | 30/12/2021 | BALAJEE ENTERPRISES | 72.05 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Chaumuha Water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08729 | Retrofitting | Emergent protection of UPVC distribution pipe line at Choumuh more of Choumah W/S scheme at Barasat II under Barasat Arsenic Division, P.H.E. Dte. (Length - 70 mtr. Approx) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000093/2021-2022 | 1830/B.Ar.D | 01/11/2021 | 01/12/2021 | IDEAL CONSTRUCTION | 4.79 | 0 | 0 | 1
4 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Chaumuha Water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08729 | Retrofitting | Emergent protection of UPVC distribution pipe line near dhokra (In between Node 44-45) of Chaumuha W/S scheme related to the work FHTCat Barasat - II under Barasat Arsenic Division, P.H.E. Dte. (Approx. Length = 70 mtr). | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000191/2021-2022 | 363/B.Ar.D | 03/03/2022 | 18/03/2022 | AT CONSTRUCTION | 4.79 | 0 | 0 | 1
5 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Chaumuha Water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08729 | Retrofitting | Repairing & Renovation of damaged Ladder of OHR & Allied works of Chowmuha Water Supply Scheme under Barasat -II block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000219/2021-2022 | 338/B.Ar.D | 28/02/2022 | 15/03/2022 | BALAJEE ENTERPRISES | 4.64 | 0 | 0 | 1
6 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Chaumuha Water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08729 | Retrofitting | Balance portion work of repairing and renovation of 02 (two) nos pump house and 01 (one) no I.E.P room and allied works at the site of Chowma W/S Scheme at Barasat-II block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000259/2021-2022 | 468/B.Ar.D | 16/03/2022 | 31/03/2022 | SANTU GHOSH | 4.78 | 0 | 0 | 1
7 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Chaumuha Water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08729 | Retrofitting | Emergent protection work of UPVC distribution pipe line near Chaumuha Chotopol (between Node 2-21) releted to the work of FHTC" of Chaumuha W/S scheme at Barasat - II under JALSWAPNA Programme under Barasat Arsenic Division, P.H.E. Dte. (Approx Lenth 70 mtr) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000148/2021-2022 | 2234/B.Ar.D | 28/12/2021 | 27/01/2022 | A. K. DUTTA & CO. | 4.79 | 0 | 0 | 0
Total | [13 empty] | 99.23 | 0 | 0