## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Emergency repair and renovation of damaged FHTC and allied work in the aftermath of Cyclonic Storm " YASS " for Atapur water supply scheme at Sandeshkhali - II block under Barasat Arsenic Division, P.H.E. Dte. (Part -3) (Sl. No.-4)¿ | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000226/2021-2022 | 1022 / B.Ar.D | 31/05/2021 | 21/06/2021 | S. K. ENTERPRISE | 4.79 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Emergency Repair & Renovation of damaged Rising main & Distribution system (CI/DI/HDPE/UPVC) due to super cyclone YASS for Atapur water supply scheme at Sandeshkhali -II block under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-1)¿ | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000216/2021-2022 | 1002/B.Ar.D | 28/05/2021 | 18/06/2021 | M/S NIRMAN CONSTRUCTION | 4.79 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Protection of UPVC distribution pipe line near at house of Sanjit Sardar (Majher Para)of Atapur W/S scheme due to Super Cyclone YASS at Sandeshkhali - II under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-1)¿ | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000229/2021-2022 | 1019/ B.Ar.D | 31/05/2021 | 21/06/2021 | ROY BISWAS CONSTRUCTION | 4.81 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Protection of UPVC distribution pipe line at Atapur Gopaler Ghat of Atapur W/S scheme due to Super Cyclone YASS at Sandeshkhali - II under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-6)¿ | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000210/2021-2022 | 1007 / B.Ar.D | 28/05/2021 | 18/06/2021 | BALAJEE ENTERPRISES | 4.74 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Emergency laying of UPVC Pipe at damaged portion from Ttimohana to Ayla Bandh of Atapur W/S scheme due to super cyclone YASS at Sandeshkhali block II under Barasat Arsenic Division, PHE Dte. (Sl. No.-2)¿ | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000242/2021-2022 | 1003 / B.Ar.D | 28/05/2021 | 18/06/2021 | PRITAM MUKHOPADHYAY | 4.34 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Protection of UPVC distribution pipe line at Atapur Aila Bandh of Atapur W/S scheme due to Super Cyclone YASS at Sandeshkhali - II under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-7)¿ | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000233/2021-2022 | 1008 / B.Ar.D | 28/05/2021 | 18/06/2021 | S. K. ENTERPRISE | 4.73 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Protection of UPVC distribution pipe line at Atapur SSK School, Majher Para (near house of Bhutta Sardar and Bholanath Sardar) of Atapur W/S scheme Due to Super Cyclone YASS at Sandeshkhali - II under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-5)¿ | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000230/2021-2022 | 1006 / B.Ar.D | 28/05/2021 | 18/06/2021 | P. & S. ASSOCIATES | 4.74 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Emergency laying of UPVC Pipe at damaged portion from Paruia More (near pump house - 1) to Taltala ghat of Atapur W/S scheme due to super cyclone YASS at Sandeshkhali block - II under Barasat Arsenic Division, PHE Dte. (Sl. No.-3)¿ | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000231/2021-2022 | 1004 / B.Ar.D | 28/05/2021 | 18/06/2021 | M/S NIRMAN CONSTRUCTION | 4.71 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Fuel and operating maintenance charges of Mobile silent type diesel generating set / Open type diesel generating set on emergency basis for two nos w/s scheme of Sandeshkhali - II block under Dist. 24 Pgs. (N). on the impending Extremely Severe cyclonic Strom¿ YASS', under Barasat Arsenic Division, PHE Dte. (Sl. No.-15)¿ | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000238/2021-2022 | 1016 / B.Ar.D | 28/05/2021 | 18/06/2021 | MONDAL ENTERPRISE | 4.01 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Protection of UPVC distribution pipe line from house of Tarun Das to H/O Pankaj Sardar (Mission Math) of Dawrir Jangle W/S scheme due to Super Cyclone YASS at Sandeshkhali - II under Barasat Arsenic Division, P.H.E. Dte.) (Sl. No.-13)¿ | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000239/2021-2022 | 1031 / B.Ar.D | 31/05/2021 | 21/06/2021 | M/S. SREEJIT ENTERPRISE | 4.66 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Protection of UPVC distribution pipe line from H/O Rafiq Molla to H/O Khalil Molla of Jeliakhali Paschim Khanda W/S scheme due to Super Cyclone YASS at Sandeshkhali - II under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-15)¿ | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000241/2021-2022 | 1033 / B.Ar.D... | 31/05/2021 | 21/06/2021 | BALAJEE ENTERPRISES | 4.74 | 0 | 0 | 0
12 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Emergency repair and renovation of damaged FHTC and allied work in the aftermath of Cyclonic Storm " YASS " for Atapur water supply scheme at Sandeshkhali - II block under Barasat Arsenic Division, P.H.E. Dte. (Part-4) (Sl. No.-5)¿ | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000204/2021-2022 | 1023/B.Ar.D | 31/05/2021 | 21/06/2021 | P & S ASSOCIATES | 4.75 | 0 | 0 | 0
13 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Protection of UPVC distribution pipe line from H/O Bidhan Mistri to H/O Goutam Mondal of Jeliakhali Paschim Khanda W/S scheme due to Super Cyclone YASS at Sandeshkhali - II under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-14)¿ | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000236/2021-2022 | 1032 / B.Ar.D | 31/05/2021 | 21/06/2021 | BALAJEE ENTERPRISES | 4.71 | 0 | 0 | 0
14 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Protection of UPVC distribution pipe line near at H/O Sontosh Patra (Majher Para) of Atapur W/S scheme due to Super Cyclone YASS at Sandeshkhali - II under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-8)¿ | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000213/2021-2022 | 1009 / B.Ar.D... | 28/05/2021 | 18/06/2021 | BALAJEE ENTERPRISES | 4.74 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Protection of UPVC distribution pipe line from H/O Sanatan Mondal to Chaitan Sarder (Part-I) at Natun Para of Dawrir jangle W/S scheme due to Super Cyclone YASS at Sandeshkhali - II under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-12)¿ | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000245/2021-2022 | 1013 / B.Ar.D | 28/05/2021 | 18/06/2021 | UTPAL CONSTRUCTION AND CO | 4.7 | 0 | 0 | 0
16 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Emergency laying of UPVC Pipe at damaged portion from Mohatali More to Gopaler Ghat of Atapur W/S scheme due to super cyclone YASS at Sandeshkhali Block II under Barasat Arsenic Division, PHE Dte. (Sl. No.-8)¿ | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000227/2021-2022 | 1026 / B.Ar.D | 31/05/2021 | 21/06/2021 | M/S NIRMAN CONSTRUCTION | 4.66 | 0 | 0 | 0
17 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Emergency repair and renovation of damaged FHTC and allied work in the aftermath of Cyclonic Storm " YASS " for Atapur water supply scheme at Sandeshkhali - II block under Barasat Arsenic Division, P.H.E. Dte. (Part -2) (Sl. No.-3)¿ | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000232/2021-2022 | 1021 / B.Ar.D | 31/05/2021 | 21/06/2021 | M/S NIRMAN CONSTRUCTION | 4.79 | 0 | 0 | 0
18 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Emergency repair and renovation of damaged FHTC and allied work in the aftermath of Cyclonic Storm " YASS " for Atapur water supply scheme at Sandeshkhali - II block under Barasat Arsenic Division, P.H.E. Dte. (Part -1). (Sl. No.-2)¿ | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000222/2021-2022 | 1020 / B.Ar.D | 31/05/2021 | 21/06/2021 | UNIFIED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.78 | 0 | 0 | 0
19 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Emergency repair and renovation of damaged Rising main & Distribution system (CI/DI/HDPE/UPVC) & FHTC including protection work and allied work in the aftermath of Cyclonic Storm " YASS " for Jeliakhali Paschim khanda water supply scheme at Sandeshkhali - II block under Barasat Arsenic Division, PHE Dte. (Sl. No.-13)¿ | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000203/2021-2022 | 1014/B.Ar.D | 28/05/2021 | 18/06/2021 | MONDAL ENTERPRISE | 4.71 | 0 | 0 | 0
20 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Emergency laying of UPVC Pipe at different damaged portion of Atapur W/S scheme due to super cyclone YASS at Sndeshkhali block II under Barasat Arsenic Division, PHE Dte. (Sl. No.-10)¿ | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000224/2021-2022 | 1011/ B.Ar.D | 28/05/2021 | 18/06/2021 | S. K. ENTERPRISE | 4.78 | 0 | 0 | 0
21 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Emergency repair and renovation of Damaged FHTC and allied work in the aftermath of Cyclonic Storm " YASS " for Atapur water supply scheme at Sandeshkhali - II block under Barasat Arsenic Division, P.H.E. Dte. (Part -5) (Sl. No.-6)¿ | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000234/2021-2022 | 1024 / B.Ar.D | 31/05/2021 | 21/06/2021 | UNIFIED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.16 | 0 | 0 | 0
22 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Emergency laying of UPVC Pipe at damaged portion at Bhyrabi Guest House and Dhuchnekhali Bazar of Atapur W/S scheme due to super cyclone YASS at Sanndeshkhali Block II under Barasat Arsenic Division, PHE Dte. (Sl. No.-11)¿ | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000235/2021-2022 | 1029 / B.Ar.D | 31/05/2021 | 21/06/2021 | BALAJEE ENTERPRISES | 4.79 | 0 | 0 | 0
23 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Emergency laying of UPVC Pipe at damaged portion from Atapur High School to Trimhona of Atapur W/S scheme due to super cyclone YASS at Sandeshkhali Block II under Barasat Arsenic Division, PHE Dte. (Sl. No.-10)¿ | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000205/2021-2022 | 1028 / B.Ar.D | 31/05/2021 | 21/06/2021 | NEW BRIGHT CONSTRUCTION | 4.78 | 0 | 0 | 0
24 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Emergency repair and renovation of damaged Rising main & Distribution system (CI/DI/HDPE/UPVC) & FHTC including protection work and allied work in the aftermath of Cyclonic Storm " YASS " for Dawrir Jangle water supply scheme at Sandeshkhali - II block under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-11)¿ | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000247/2021-2022 | 1012 / B.Ar.D... | 28/05/2021 | 18/06/2021 | UTPAL CONSTRUCTION AND CO | 4.65 | 0 | 0 | 0
25 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Protection of UPVC distribution pipe line at Taltalaghat of Atapur W/S scheme Due to Super Cyclone YASS at Sandeshkhali - II under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-9) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000301/2021-2022 | 1010/B.Ar.D | 28/05/2021 | 18/06/2021 | DEEP EXERTION | 4.39 | 0 | 0 | 0
26 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Emergency laying of UPVC Pipe at damaged portion at Gurumali Para & Kasari Para of Jeliakhali Paschim Khanda W/S scheme due to super cyclone YASS at Sandeshkhali Block II under Barasat Arsenic Division, PHE Dte. (Sl. No.-16)¿ | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000200/2021-2022 | 1033 /A / B.Ar.D | 31/05/2021 | 21/06/2021 | PREMANANDA ROY BISWAS | 4.77 | 0 | 0 | 0
27 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Protection of UPVC distribution pipe line from house of Kinkar Das to H/O Tarun Das (Mission Math) of Dawrir Jangle W/S scheme due to Super Cyclone YASS at Sandeshkhali - II under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-12)¿ | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000237/2021-2022 | 1030 / B.Ar.D | 31/05/2021 | 21/06/2021 | M/S. SREEJIT ENTERPRISE | 4.7 | 0 | 0 | 0
28 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Protection of UPVC distribution pipe line at different places of Jeliakhali Paschim Khnda W/S scheme due to Super Cyclone YASS at Sandeshkhali - II under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-14)¿ | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000225/2021-2022 | 1015/ B.Ar.D | 28/05/2021 | 18/06/2021 | THREE MAA ENTERPRISE | 4.71 | 0 | 0 | 0
29 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Supply Delivery and Distriction of Miscellaneous Stationery item and Refresment in connection with High Level meeting /assembly/congreation /conventions/discussions etc . at PHED Hedquaters office at Kolkata (Sl No-01) | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000272/2021-2022 | 1143/B.Ar.D. | 13/07/2021 | 09/01/2022 | CALCON CONSTRUCTIONS | 4.97 | 0 | 0 | 0
30 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Emergency repair and renovation of Damaged Road and allied work in the aftermath of Cyclonic Storm " YASS " for Atapur water supply scheme at Sandeshkhali - II block under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-7)¿ | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000228/2021-2022 | 1025 / B.Ar.D | 31/05/2021 | 21/06/2021 | M/S NIRMAN CONSTRUCTION | 4.71 | 0 | 0 | 100
31 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte | SM/08996 | Disaster | Emergency laying of UPVC Pipe at damaged portion from Trimohanna (near house of Monoranjan Mondal ) to Das Para of Atapur W/S scheme due to super cyclone YASS at Sandeshkhali Block II under Barasat Arsenic Division, PHE Dte. (Sl. No.-9)¿ | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000240/2021-2022 | 1027 / B.Ar.D | 31/05/2021 | 21/06/2021 | BALAJEE ENTERPRISES | 4.71 | 0 | 0 | 100
Total | [13 empty] | 145.04 | 0 | 0