## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Extension of Piped Water Supply (PWS) to Anganwadi Centre (AWCs 56 Nos.) located within the command area of PWS schemes under Barasat Arsenic Division, PHE Dte | SM/09039 | Anganwadi | Arrangement of Drinking Water for Anganwadi Center having Electrical Power connection and located within Command area of Piped Water supply scheme (PWSS) for Sandeshkhali -II Block of North 24 Pgs district under Barasat Arsenic Division, PHE Dte. (Type -IA Electrical Power Operated) | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000106/2021-2022 | 1935/B.Ar.D. | 18/11/2021 | 18/12/2021 | MONDAL ENTERPRISE | 13.96 | 13.96 | 99.98 | 0
2 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Extension of Piped Water Supply (PWS) to Anganwadi Centre (AWCs 56 Nos.) located within the command area of PWS schemes under Barasat Arsenic Division, PHE Dte | SM/09039 | Anganwadi | Arrangement of Drinking Water for Anganwadi Center having Electrical Power connection and located within Command area of Piped Water supply scheme (PWSS) for Rajarhat Block of North 24 Pgs district under Barasat Arsenic Division, PHE Dte. (Type -IA Electrical Power Operated). | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000108/2021-2022 | 1937/B.Ar.D. | 18/11/2021 | 02/01/2022 | N. H. ENTERPRISE | 21.11 | 19.55 | 92.61 | 0
3 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Extension of Piped Water Supply (PWS) to Anganwadi Centre (AWCs 56 Nos.) located within the command area of PWS schemes under Barasat Arsenic Division, PHE Dte | SM/09039 | Anganwadi | Arrangement of Drinking Water for Anganwadi Center having Electrical Power connection and located within Command area of Piped Water supply scheme (PWSS) for Baduria, Hasnabad of North 24 Pgs district under Barasat Arsenic Division, PHE Dte. (Type -IA Electrical Power Operated) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000107/2021-2022 | 1936/B.Ar.D. | 18/11/2021 | 18/12/2021 | MAHALAXMI CONSTRUCTION | 13.25 | 13.24 | 99.89 | 0
Total | [13 empty] | 48.32 | 46.74 | 96.74