## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Chowlpur water supply scheme for providing FHTC under Barasat Arsenic Division, P.H.E. Dte. (Phase - III) | SM/09934 | Retrofitting | Providing Functional Household Tap Connection (FHTC) and allied works at left out portion of different Mouzas under command area of Chowlpur W/S scheme of Barasat - II blocks from Chowlpur and it adjoining mouzas ground water supply scheme under "JAL SWAPNA" programme under Barasat Arsenic Division, PHE Dte. (Phase - III). | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000173/2021-2022 | 254/B.Ar.D. | 17/02/2022 | 18/05/2022 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 81.34 | 43.28 | 53.21 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Chowlpur water supply scheme for providing FHTC under Barasat Arsenic Division, P.H.E. Dte. (Phase - III) | SM/09934 | Retrofitting | Repair & Renovation of Iron Elimination Plant of 69 M3 including Media Change of Chowlpur Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000049/2022-2023 | 1352/B.Ar.D | 22/07/2022 | 21/08/2022 | WATERCOMP INDIA | 4.74 | 4.71 | 99.35 | 1
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Chowlpur water supply scheme for providing FHTC under Barasat Arsenic Division, P.H.E. Dte. (Phase - III) | SM/09934 | Retrofitting | Restoration due to laying of various dia UPVC/HDPE Pipe distribution line at Malrameswarpur mouza of Chowlpur W/S Scheme under Barasat -II block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000204/2023-2024 | 3030/B.Ar.D. | 29/12/2023 | 28/01/2024 | SIRCON ENGINEERING SERVICES | 7.69 | 7.63 | 99.22 | 100
Total | [13 empty] | 93.77 | 55.62 | 59.31