## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10549 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II under Paltadanga W/S Scheme District of North 24 Pgs. NIET No.- 12 of EE/EMD of 2022-23 (Sl. No.-04) | Assistant Engineer | Junior Engineer | ORD/000094/2022-2023 | 5091/EMD | 04/11/2022 | 04/12/2022 | MAHAMAYA ENTERPRISE. | 11.17 | 6.66 | 59.66 | 60
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10549 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I under Paltadanga W/S Scheme District of North 24 Pgs. NIET No.- 12 of EE/EMD of 2022-23 (Sl. No.- 03) |  | Junior Engineer | ORD/000093/2022-2023 | 5090/EMD | 04/11/2022 | 04/12/2022 | KASHINATH PAL & CO. | 11.29 | 8.78 | 77.75 | 78
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10549 | Augmentation | Hiring of one (1) no. Diesel operated AC motor cab / maxi cab (Car No. - WB-08C-5757) with engine capacity less than or equal to 2000 C.C. with driver for official use of the Chief Engineer (Head Quarters), PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for six months (w.e.f. 02.01.2023 to 02.07.2023). | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000183/2022-2023 | 2550/B.Ar.D | 29/12/2022 | 29/06/2023 | RANA PAUL | 0.95 | 2.39 | 252.33 | 0
4 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10549 | Augmentation | Hiring of one (1) no. Diesel operated motor cab (WB-07J-7190) with driver for official use for Deputy Superintending Engineer, PIU, North 24 Pgs., WBDWSIP, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for six months (w.e.f. 09.01.2023 to 09.07.2023). | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000178/2022-2023 | 2512/B.Ar.D | 23/12/2022 | 23/06/2023 | PRIYANKI SADHUKHAN | 0.86 | 1.34 | 155.33 | 100
5 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10549 | Augmentation | Preparation of Augmentation DPR for Paltadanga Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000120/2022-2023 | 1957/B.Ar.D | 26/09/2022 | 16/10/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.99 | 0.98 | 98.99 | 1
6 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10549 | Augmentation | Hiring of one (1) no. Diesel operated motor cab (Car No.- WB-20BP-9500) with driver for official use for Deputy Superintending Engineer, Eastern Circle, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for six months (w.e.f. 01.01.2023 to 01.07.2023). | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000182/2022-2023 | 2549/B.Ar.D | 29/12/2022 | 29/06/2023 | RAJ ENTERPRISE | 0.86 | 2.15 | 248.89 | 1
7 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10549 | Augmentation | Laying of distribution System including specials , valves all complete Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Paltadanga under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Division,Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000092/2022-2023 | 1708/B.Ar.D. | 02/09/2022 | 30/11/2025 | M/S. S. S. ENTERPRISE | 344.61 | 311.65 | 90.43 | 98
8 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10549 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2022-2023 | 2105/B.Ar.D. | 02/11/2022 | 02/11/2022 | Resource Division | 12.6 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10549 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2022-2023 | 2291/B.Ar.D | 02/12/2022 | 02/12/2022 | Resource Division | 146.5 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10549 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 300 Mtrs. Depth) by utilising Departmental Machineries for Paltadanga W/S Scheme (TW-I), Barasat-II Block under North 24 Pgs. District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000151/2023-2024 | 1647/CDD | 17/10/2023 | 16/11/2023 | SUBHRA ENTERPRISE | 21.79 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10549 | Augmentation | Repair and Renovation works of R.C.C. Elevated Reservoir of Capacity 550 CUM at Paltadanga W/S Scheme of Barasat - II block under Barasat Arsenic Division PHE Dte. | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000206/2022-2023 | 466/B.Ar.D. | 27/02/2023 | 28/04/2023 | G. S. CONSTRUCTION & CO. | 19.14 | 18.21 | 95.15 | 100
12 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10549 | Augmentation | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab (Car No.- WB-20BP-9500) with driver for official use for Deputy Superintending Engineer, Eastern Circle, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for six months (w.e.f. 02.07.2023 to 30.12.2023)". |  | Junior Engineer | ORD/000151/2023-2024 | 1535/B.Ar.D | 30/06/2023 | 29/12/2023 | RAJ ENTERPRISE | 0.86 | 2.26 | 261.16 | 100
13 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10549 | Augmentation | Wayleave facility charges from Stn. Sondalia to Beliaghata Road Halt |  |  | BILL/00164/2023-2024 | 237 | 16/08/2023 | 16/08/2023 | RAIL BHOOMI CROSSING SEVA (IR-RBCS) | 15.24 | 0 | 0 | 0
14 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10549 | Augmentation | Wayleave plan & survey charges |  |  | BILL/00118/2023-2024 | 180 | 24/07/2023 | 24/07/2023 | RAIL BHOOMI CROSSING SEVA (IR-RBCS) | 0.21 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10549 | Augmentation | Road Restoration of Aminpur - Boalghata road due to Laying of different dia UPVC pipe line under Paltadanga W/S Scheme at Barasat-II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000073/2024-2025 | 1848/B.Ar.D | 21/11/2024 | 12/12/2024 | P & S ASSOCIATES | 0.94 | 0 | 0 | 100
16 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10549 | Augmentation | Recycling of IEP Back Wash with its ancillaries works at the site of Paltadanga W/S Scheme under augmentation Scheme at Barasat-II Block North 24 pgs. District under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000220/2023-2024 | 384/B.Ar.D. | 21/02/2024 | 15/02/2025 | M/S B. B. ENGINEERING | 11.16 | 0 | 0 | 100
17 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10549 | Augmentation | Supplying, Laying, fitting and fixing of DI pipe and Repairing, Renovation and protection of boundary wall, Fencing work etc. and other allied works at Head work site of Paltadanga Ground Water Based Piped W/S Scheme under Barasat-II Block under Barasat Arsenic Division PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000228/2023-2024 | 389/B.Ar.D | 21/02/2024 | 24/10/2024 | NIKHIL SAMADDAR | 19.27 | 16.06 | 83.34 | 70
18 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10549 | Augmentation | Restoration due to laying of various dia UPVC/HDPE Pipe for distribution line at Bharpara Baramallika mouza of Paltadanga W/S Scheme under Barasat -II block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000074/2024-2025 | 1849/B.Ar.D | 21/11/2024 | 21/12/2024 | BALAJEE ENTERPRISES | 0.92 | 0 | 0 | 100
19 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10549 | Augmentation | Supplying, Laying, Fitting, fixing and jointing of different dia UPVC pipe line for distribution network and other allied works at Head work site of Paltadanga W/S Scheme under Barasat Arsenic Division PHE Dte. (SM/10549) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000142/2024-2025 | 295/B.Ar.D. | 18/02/2025 | 20/11/2025 | N. H. ENTERPRISE | 17.94 | 0 | 0 | 100
Total | [13 empty] | 637.3 | 370.48 | 58.13