## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10551 | Augmentation | Preparation of Augmentation DPR for Puturia Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000117/2022-2023 | 1953/B.Ar.D | 26/09/2022 | 16/10/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.99 | 0.99 | 99.84 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10551 | Augmentation | Hiring of Contract carriage (BS-IV) of the office use of the DSE PIU N24PGS WBDWSIP PHE DTE. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000161/2022-2023 | 1402//B.Ar.D | 29/07/2022 | 29/01/2023 | BISWADIP SIKDAR | 0.87 | 0.4 | 45.43 | 1
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10551 | Augmentation | construction order No - Horing of one (1) No Diseal Operated Motor Cab ( Car No -WB-25K-2915) with driver for offical use for Assistent Engineer (HQ-I) ,Barasat Arsenic Divisuion ,PHE Dte with all costs towards the owner except fuel cost i.e Diesel & Mobil oil for the period from 01.05.2022 to 30.04.2023 | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000180/2022-2023 | 796//B.Ar.D | 26/04/2022 | 26/04/2023 | PREMANANDA ROY BISWAS | 1.73 | 0 | 0 | 100
4 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10551 | Augmentation | Submission of all documents regarding crossing of Railway track for laying Water Pipe line main for Puturia W/S Scheme in between Sondalia & Beliaghata Road Railway Station on Barasat - Hasnabad Section under Barasat-II Block. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000234/2022-2023 | 747/B.Ar.D. | 24/03/2023 | 08/04/2023 | P & S ASSOCIATES | 1.96 | 1.96 | 100 | 0
5 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10551 | Augmentation | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab (AC) (Car No. WB-25F-6815) with driver for official use for Chief Engineer (Head Quarters) in place of Director,WSSO, PHE Department. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 22.08.2022 to 21.02.2023." | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000066/2022-2023 | 1520/B.Ar.D | 18/08/2022 | 18/02/2023 | NASIRUDDIN BISWAS | 0.96 | 0.79 | 82.82 | 1
6 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10551 | Augmentation | Hiring charges of vehicle. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000328/2021-2022 | 3812/EC | 30/12/2021 | 30/12/2022 | PRABIR RONG | 1.73 | 0 | 0 | 1
7 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10551 | Augmentation | CONTINUATION ORDER for ''Hiring of one (1) no Diesel operated Motor cab 9Non AC) Car No WB-11C 8013) with driver for offical use for Chief Engineer & Director ,WSSO. PHE Department with all costs towards the owner excpet fuel cost i.e. Diesel & Mobil oil for the period from 22.08.2022 to 21.02.2023.'' | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000170/2022-2023 | 1521 //B.Ar.D | 18/08/2022 | 18/02/2023 | GOUR HARI SAHOO | 0.86 | 1.11 | 130.15 | 1
8 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10551 | Augmentation | Continuation order for -Hiring of One (1) no Diesel operated cab (Car no-WB-25K-2915) with driver for offical use for Assistent Engineer (HQ-II) Barasat Arsenic Division PHE Dte with all cost towards the owner except fuel cost i.e Diesel & Mobil oil for the period from 01.05.2022 to 30.04.2023 | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000181/2022-2023 | 796/ B.Ar.D | 26/04/2022 | 26/04/2023 | PREMANANDA ROY BISWAS | 1.73 | 3.06 | 176.55 | 1
9 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10551 | Augmentation | Eucalyptus Bullah piling for Protection of UPVC distribution pipe line at Bokanda Ghosh Para of Puturia W/S Scheme under Barasat- II Block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000210/2022-2023 | 472/B.Ar.D. | 27/02/2023 | 29/03/2023 | KAKALI ENTERPRISE | 10.72 | 10.7 | 99.75 | 100
10 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10551 | Augmentation | Submission of all documents regarding crossing of Railway track for laying Water Pipe line main for Surface Based PWSS for Barasat-II Block in between Sondalia & Beliaghata Road Railway Station on Barasat - Hasnabad Section. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000235/2022-2023 | 748/B.Ar.D. | 24/03/2023 | 08/04/2023 | P & S ASSOCIATES | 1.96 | 1.96 | 100 | 100
11 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10551 | Augmentation | Repair and Renovation works of Existing R.C.C. Elevated Reservoir & other existing civil component of Capacity 700 Cu.m. at Puturia W/S Scheme uder Barasat-II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000022/2023-2024 | 948/B.Ar.D. | 17/04/2023 | 16/06/2023 | MONDAL ENTERPRISE | 16.73 | 14.13 | 84.46 | 100
12 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10551 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000026/2022-2023 | 26/B.Ar.D. | 05/01/2023 | 05/01/2023 | Resource Division | 14.73 | 0 | 0 | 0
13 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10551 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000032/2022-2023 | 204/B.Ar.D. | 30/01/2023 | 30/01/2023 | Resource Division | 258.81 | 0 | 0 | 0
14 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10551 | Augmentation | Wayleave facility charges Sondalia to Beliaghata Road Halt |  |  | BILL/00166/2023-2024 | 236 | 16/08/2023 | 16/08/2023 | RAIL BHOOMI CROSSING SEVA (IR-RBCS) | 5.95 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10551 | Augmentation | Wayleave plan & survey charges (Stn.Sondalia to Beliaghata Road Halt) |  |  | BILL/00116/2023-2024 | 181 | 24/07/2023 | 24/07/2023 | RAIL BHOOMI CROSSING SEVA (IR-RBCS) | 0.07 | 0 | 0 | 0
16 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10551 | Augmentation | Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Puturia under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000135/2022-2023 | 1743/B.Ar.D. | 07/09/2022 | 06/12/2022 | S. P. CONSTRUCTION | 382.09 | 292.34 | 76.51 | 100
17 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10551 | Augmentation | Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Mochpol mouza for Augmentation of Ground Based Water Supply Scheme at Puturia under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000233/2023-2024 | 394/B.Ar.D | 21/02/2024 | 27/11/2024 | THREE MAA ENTERPRISE | 46.15 | 19.53 | 42.32 | 100
18 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10551 | Augmentation | Sinking for 1 nos 250 mm. x 150 mm. dia. 270 mtr deep Tubewell by D.R. Rig method with UPVC pipe & strainer having 250 mm dia 42 mtr. long housing pipe & 150 mm dia 30 mtr. long filter at Puturia W/S Scheme of Barasat-II block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000017/2024-2025 | 997/B.Ar.D. | 19/06/2024 | 04/10/2024 | B. S. ENTERPRISE | 13.46 | 11.79 | 87.58 | 100
19 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10551 | Augmentation | Payment of quotation amount for new service connection at P/H No: IV under Puturia water supply scheme , Block: Barasat-II. |  |  | BILL/01849/2024-2025 | BP-162-24-25 | 14/11/2024 | 14/11/2024 | W.B.S.E.D.C.L (KADAMBAGACHI C.C.C) | 2.73 | 0 | 0 | 0
20 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10551 | Augmentation | Hiring of one (1) no. Diesel / Petrol operated motor cab (car No. WB19J 2141) with driver for official use for Assistant Engineer (HQ ¿ I), Barasat Arsenic Division, PHE Dte. w.e.f. 01.01.2025 to 30.06.2025. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000102/2024-2025 | 2069/B.Ar.D. | 16/12/2024 | 15/06/2025 | OM ENTERPRISE | 0.86 | 0.79 | 92.05 | 0
21 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10551 | Augmentation | Construction of 4.88 mtr. x 3.6 mtr. size new Pump House (Pump House-IV) with Boundary Wall and Allied Works for PUTURIA W/S Scheme Under Barasat Arsenic Division, PHE Dte. (SM/10551) | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000147/2024-2025 | 329/B.Ar.D. | 27/02/2025 | 28/04/2025 | GRAVITA ENTERPRISE | 9.11 | 0 | 0 | 100
22 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10551 | Augmentation | Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for within leftout area of Falti and Bamandanga area for the scheme 'Augmentation of Ground Based Water Supply Scheme at Puturia under Barasat - II Block under Barasat Arsenic Division, PHE Dte'. (SM/10551) | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000004/2025-2026 | 796/B.Ar.D. | 30/04/2025 | 27/10/2025 | TOJO ENTERPRISE | 41.81 | 0 | 0 | 100
23 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/10551 | Augmentation | CONTINUATION ORDER for "Hiring of one (1) no. Diesel / Petrol operated motor cab (Car No.- WB19J - 2141) with driver for official use for Assistant Engineer (HQ-I), Barasat Arsenic Division, PHE Dte. (w.e.f. 01.07.2025 to 30.11.2025)". | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000052/2025-2026 | 1123/B.Ar.D | 25/06/2025 | 25/11/2025 | OM ENTERPRISE | 0.73 | 0 | 0 | 0
Total | [13 empty] | 816.74 | 359.55 | 44.02