## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Magurati Srirampur W/S Scheme for providing FHTC under Barasat Arsenic Division, PHE Dte. (Phase - II) | SM/10559 | Augmentation | Sinking of 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter for Augmentation at 2nd T/W site of Magurati Srirampur w/s scheme of Baduria block under Barasat Arsenic Division, P.H.E. Dte. (Sl No. 2) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000027/2022-2023 | 1106/B.Ar.D. | 17/06/2022 | 01/08/2022 | ACME CONSTRUCTION | 14.61 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Magurati Srirampur W/S Scheme for providing FHTC under Barasat Arsenic Division, PHE Dte. (Phase - II) | SM/10559 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II underMagurati Srirampur W/S Scheme District of 24 Pgs. (N) (Block- Baduria). NIET No.- 15 of EE/EMD of 2022-23 (Sl. No.- 07) | Assistant Engineer | Junior Engineer | ORD/000117/2022-2023 | 6144/EMD | 11/11/2022 | 11/12/2022 | R.N.S. TRADING | 12.8 | 0 | 0 | 100
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Magurati Srirampur W/S Scheme for providing FHTC under Barasat Arsenic Division, PHE Dte. (Phase - II) | SM/10559 | Augmentation | Laying of UPVC pipe line for Providing Functional House Hold Tap Connection under command area of Magurati Srirampur water supply scheme of Baduria Block under JJM Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000191/2022-2023 | 243/B.Ar.D. | 02/02/2023 | 04/03/2023 | UMA CONSTRUCTION | 13.6 | 0 | 0 | 90
Total | [13 empty] | 41.01 | 0 | 0