## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11544 | Augmentation | Preparation of Augmentation DPR for Bahira Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000119/2022-2023 | 1956/B.Ar.D | 26/09/2022 | 16/10/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.99 | 0.98 | 99.68 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11544 | Augmentation | Laying of distribution System including specials, valves all complete Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Bahira under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000136/2022-2023 | 1742/B.Ar.D. | 07/09/2022 | 06/12/2022 | MADE AND TRADE CO. | 311.1 | 253.32 | 81.43 | 72
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11544 | Augmentation | Sinking of 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method near H/W Side with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter for Augmentation of Bahira w/s scheme of Barasat-II block under Barasat Arsenic Division, P.H.E. Dte. (Sl No. 1) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000131/2022-2023 | 2055/B.Ar.D. | 19/10/2022 | 03/12/2022 | UNIFIED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 15.58 | 13.76 | 88.32 | 70
4 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11544 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2022-2023 | 205/B.Ar.D. | 30/01/2023 | 30/01/2023 | Resource Division | 16.41 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11544 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2022-2023 | 28/B.Ar.D. | 05/01/2023 | 05/01/2023 | Resource Division | 12.26 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11544 | Augmentation | Hiring of one (1) no. Diesel operated motor cab (Car No.- WB25L-3454) with driver for official use for Assistant Engineer (Sub-Division), under Barasat Arsenic Division, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil w.e.f. 01.05.2023 to 16.11.2023. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000026/2023-2024 | 1008/B.Ar.D | 26/04/2023 | 12/11/2023 | PREMANANDA ROY BISWAS | 0.95 | 2.3 | 241.92 | 70
7 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11544 | Augmentation | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab (Car No.- WB-25L-3454) with driver for official use for Assistant Engineer (Sub-Division), under Barasat Arsenic Division, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil w.e.f. 17.11.2023 to 30.11.2023". | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000177/2023-2024 | 2661/B.Ar.D | 09/11/2023 | 23/11/2023 | PREMANANDA ROY BISWAS | 0.07 | 0.16 | 247.8 | 0
8 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11544 | Augmentation | Sal-Bullah Pilling for pipe protection work at Bahira under Barasat-II Block Under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000007/2024-2025 | 981/B.Ar.D. | 18/06/2024 | 13/07/2024 | CHAKRABORTY SUPPLIERS & CONSTRUCTION | 5.85 | 5.81 | 99.36 | 100
9 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11544 | Augmentation | Repair and Renovation works of Existing R.C.C. Elevated Reservoir & other existing civil component of Capacity 550 Cu.m. at Bahira W/S Scheme under Barasat-II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000187/2022-2023 | 237/B.Ar.D. | 02/02/2023 | 23/05/2025 | MONDAL ENTERPRISE | 16.32 | 10.13 | 62.09 | 40
10 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11544 | Augmentation | Inter connection of pump with Existing IEP and other allied works of Bahira W/S Scheme Barasat-II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division,Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000167/2024-2025 | 429/B.Ar.D. | 10/03/2025 | 09/04/2025 | S.B.S. ENTERPRISE | 2.5 | 0 | 0 | 100
11 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11544 | Augmentation | Damage pipeline laying and other allied works of Bahira W/S Scheme Barasat-II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000188/2024-2025 | 427/B.Ar.D. | 10/03/2025 | 09/04/2025 | S.B.S. ENTERPRISE | 3.93 | 0 | 0 | 100
Total | [13 empty] | 385.96 | 286.48 | 74.22