## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11545 | Augmentation | Preparation of Augmentation DPR for Chowmuha Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000118/2022-2023 | 1954/B.Ar.D | 26/09/2022 | 16/10/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.99 | 0.99 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11545 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000028/2022-2023 | 29/B.Ar.D. | 05/01/2023 | 05/01/2023 | Resource Division | 1.53 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11545 | Augmentation | Emergent Protection of 90 mm dia UPVC Pipeline in between Node 459-460&106-107 related to the work " Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Chaumuha Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte." (60mtr) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000148/2023-2024 | 2374/B.Ar.D. | 27/09/2023 | 27/10/2023 | NEELAM ENTERPRISE | 5.89 | 5.88 | 99.82 | 100
4 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11545 | Augmentation | Emergent Protection of 90 mm dia UPVC Pipeline in between Node 459-460 & 106-107 related to the work "Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Chaumuha Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte." (60mtr). | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000173/2023-2024 | 2658/B.Ar.D. | 09/11/2023 | 09/12/2023 | MONDAL ENTERPRISE | 5.93 | 5.88 | 99.21 | 100
5 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11545 | Augmentation | Emergent Protection of 90 mm dia UPVC Pipeline in between Node 374-376 related to the work " Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Chaumuha Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000200/2023-2024 | 3029/B.Ar.D. | 29/12/2023 | 28/01/2024 | RHINE CONSTRUCTION | 4.63 | 4.61 | 99.57 | 100
6 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11545 | Augmentation | Laying of 200 mm dia D.I rising main from 2nd Tubewell to Head work site of Chaumuha W/S scheme at Barasat - II under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000202/2023-2024 | 3007/B.Ar.D | 28/12/2023 | 18/01/2024 | R. UNIQUE CONSTRUCTION | 0.93 | 0.92 | 98.93 | 100
7 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11545 | Augmentation | Repair and Renovation works of 250 Cum OHR and allied water supply component infrastructure under Chaumuha W/S Scheme of Barasat -II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000196/2023-2024 | 3026/B.Ar.D. | 29/12/2023 | 12/02/2024 | BANERJEE CONSTRUCTION | 19.55 | 19.41 | 99.29 | 100
8 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11545 | Augmentation | Increse of Water pressure through by pass Pipeline from Second tubewell to main distribution pipeline and allied repairing works in Chaumuha Water Supply Scheme under Barasat Arsenic Division, P.H.E Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000009/2024-2025 | 983/B.Ar.D. | 18/06/2024 | 09/07/2024 | BANERJEE CONSTRUCTION | 2.53 | 2.35 | 93.22 | 100
9 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11545 | Augmentation | Restoration of Road due to Laying of 200 mm dia D.I rising main from 2nd Tubewell to Head work site at Chaumuha Purbapara of Chaumuha W/S scheme at Barasat - II under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000071/2024-2025 | 1847/B.Ar.D | 21/11/2024 | 12/12/2024 | R. UNIQUE CONSTRUCTION | 0.95 | 0.93 | 98.35 | 100
10 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11545 | Augmentation | Payment of quotation for new service connection at P/H - III under Chaumuha water supply scheme. Dist: 24 Pgs (North) |  |  | BILL/05031/2023-2024 | BP-338-23-24 | 11/03/2024 | 11/03/2024 | W.B.S.E.D.C.L (KADAMBAGACHI C.C.C) | 2.06 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11545 | Augmentation | Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Chaumuha Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000087/2022-2023 | 1557/B.Ar.D. | 24/08/2022 | 09/02/2025 | BANERJEE CONSTRUCTION | 168.13 | 131.79 | 78.39 | 90
12 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11545 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 32.79 | 0.15 | 11
13 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11545 | Augmentation | Outdoor illumination by supplying and installing of 15 watt solar street Light at PH- I under Chaumuha W/S Scheme, Barasat-II Block, Dist.- 24 pgs (N) under Eastern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001551/2024-2025 | 341/EMSD-I | 11/03/2025 | 10/04/2025 | M/S GHOSH ENTERPRISE | 2.72 | 0 | 0 | 0
Total | [13 empty] | 21555.59 | 205.55 | 0.95