## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11557 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2022-2023 | 2211/B.Ar.D. | 22/11/2022 |  | Resource Division | 16.29 | 0 | 0 | 0
2 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11557 | Augmentation | Preparation of Augmentation DPR for Rohanda Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000115/2022-2023 | 1951/B.Ar.D | 26/09/2022 | 16/10/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.99 | 0.99 | 100 | 1
3 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11557 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000030/2022-2023 | 30/B.Ar.D. | 05/01/2023 |  | Resource Division | 16.27 | 0 | 0 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11557 | Augmentation | Sinking of 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter for Augmentation of Rohanda w/s scheme of Barasat-II block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000039/2022-2023 | 1221/B.Ar.D. | 05/07/2022 | 19/08/2022 | ACME CONSTRUCTION | 14.82 | 13.66 | 92.16 | 1
5 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11557 | Augmentation | Repair and Renovation works of Existing R.C.C. Elevated Reservoir & other existing civil component of Capacity 450 Cu.m. at Rohanda W/S Scheme uder Barasat-II Block under Barasat Arsenic Division, PHE Dte. (SM/11557) | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000157/2022-2023 | 2469/B.Ar.D. | 21/12/2022 | 19/02/2023 | M.R.CONSTRUCTION | 14.74 | 14.05 | 95.35 | 1
6 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11557 | Augmentation | New Service Connection of WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. for the month of April under Rohanda W/S Scheme. |  |  | BILL/00420/2023-2024 | 39/PFMS/EMD | 18/05/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.97 | 0 | 0 | 0
7 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11557 | Augmentation | Construction of 3.6 mtr. x 3.0 mtr. size new Pump House ( Pump House-III ) with sanitary arrangement, construction of boundary wall and Allied Works for ROHANDA W/S Scheme Under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000213/2022-2023 | 469/B.Ar.D. | 27/02/2023 | 28/04/2023 | PRAGATI CONSTRUCTION & CO | 11.55 | 7.52 | 65.11 | 90
8 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11557 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Rep.) under Rohanda W/S Scheme with Pump House No-I under Choumuha W/S scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001724/2023-2024 | 4533-EMD | 19/07/2023 | 18/08/2023 | M/S. S.G. ENTERPRISE | 31.91 | 9.62 | 30.15 | 30
9 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11557 | Augmentation | Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Rohanda under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000091/2022-2023 | 1711/B.Ar.D. | 02/09/2022 | 01/12/2022 | GARGO TRADERS | 406.42 | 395.87 | 97.4 | 94
10 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11557 | Augmentation | Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within Kachua, Noapara and Singhpara area for Augmentation of Ground Based Water Supply Scheme at Rohanda under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000238/2023-2024 | 536/B.Ar.D. | 13/03/2024 | 12/04/2024 | TOJO ENTERPRISE | 24.34 | 12.02 | 49.38 | 5
11 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11557 | Augmentation | Hiring of one (1) no. Diesel operated AC motor cab / maxi cab (Car No. WB-25F-6815) with engine capacity less than or equal to 2000 C.C. with driver for official use of the Chief Engineer (Head Quarters), Office, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 01.12.2023 to 07.06.2024. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000167/2023-2024 | 2696/B.Ar.D | 23/11/2023 | 31/05/2024 | TOJO ENTERPRISE | 0.99 | 2.49 | 251.94 | 64
12 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11557 | Augmentation | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated AC motor cab / maxi cab (Car No. WB-25F-6815) with engine capacity less than or equal to 2000 C.C. with driver for official use of the Chief Engineer (Head Quarters), Office, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 08.06.2024 to 30.06.2024". | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000021/2024-2025 | 944/B.Ar.D | 06/06/2024 | 29/06/2024 | TOJO ENTERPRISE | 0.12 | 0.3 | 248.04 | 0
Total | [13 empty] | 539.41 | 456.53 | 84.63