## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11558 | Augmentation | Preparation of Augmentation DPR for Bagband Saiberia Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000121/2022-2023 | 1958/B.Ar.D | 26/09/2022 | 16/10/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.99 | 0.98 | 99.68 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11558 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2022-2023 | 2212/B.Ar.D. | 22/11/2022 | 22/11/2022 | Resource Division | 20.91 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11558 | Augmentation | Repair and Renovation works of Existing R.C.C. Elevated Reservoir & other existing civil component of Capacity 800 Cu.m. at Bagband Saiberia W/S Scheme uder Barasat-II Block under Barasat Arsenic Division, PHE Dte. (SM/11558) | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000156/2022-2023 | 2468/B.Ar.D. | 21/12/2022 | 19/02/2023 | SAHA ENTERPRISE | 16.6 | 15.13 | 91.13 | 60
4 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11558 | Augmentation | Sinking of 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter for Augmentation of Bagband Saiberia w/s Scheme at Nababpur Mouza of Barasat-II block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000214/2022-2023 | 468/B.Ar.D. | 27/02/2023 | 13/04/2023 | AUXILIARY TUBEWELL DRILLERS | 15.62 | 11.81 | 75.63 | 100
5 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11558 | Augmentation | Sinking of 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter for Augmentation of Bagband Saiberia w/s Scheme at Kayemba Mouza of Barasat-II block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000009/2023-2024 | 920/B.Ar.D. | 11/04/2023 | 26/05/2023 | ACME CONSTRUCTION | 15.62 | 12.77 | 81.74 | 100
6 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11558 | Augmentation | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab (AC) (Car No. WB-25F-6815) with driver for official use for Chief Engineer (Head Quarters) in place of Director, WSSO, PHE Department. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 01.06.2023 to 31.08.2023." | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000040/2023-2024 | 1281/B.Ar.D | 30/05/2023 | 30/08/2023 | NASIRUDDIN BISWAS | 0.48 | 1.19 | 249.2 | 100
7 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11558 | Augmentation | Yard lighting arrangement at the premises of P.H No.-I (Head works site) under Bagband Saiberia W/S Scheme, Dist-24Pgs (N). |  |  | ORD/002862/2022-2023 | 748/EMSD-I | 14/03/2023 | 03/04/2023 | PURUSHOTTAM ENTERPRISE | 3.02 | 2.81 | 93.08 | 90
8 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11558 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000031/2022-2023 | 31/B.Ar.D. | 05/01/2023 | 05/01/2023 | Resource Division | 20.91 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11558 | Augmentation | Deposit work other than new Service connection at PH-V bagbanda Saiberia Khamarpara W/S Scheme |  |  | BILL/03617/2023-2024 | BP-227-23-24 | 21/11/2023 | 21/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.54 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11558 | Augmentation | New Service connection at PH-V bagbanda Saiberia Kemia Khamarpara W/S Scheme |  |  | BILL/03616/2023-2024 | BP-228-23-24 | 21/11/2023 | 21/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.97 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11558 | Augmentation | Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Bagband Saiberia under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000093/2022-2023 | 1721/B.Ar.D. | 05/09/2022 | 27/05/2024 | PUSPA ENTERPRISE | 442.01 | 261.38 | 59.14 | 86
12 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11558 | Augmentation | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab (Car No. WB-25L-0302) with driver for official use for Executive Engineer, Barasat Arsenic Division, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 01.04.2023 to 30.04.2023." | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000227/2022-2023 | 827/B.Ar.D | 30/03/2023 | 29/04/2023 | RANJIT KUMAR MONDAL | 0.14 | 0.36 | 251.39 | 0
13 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11558 | Augmentation | Hiring of one (1) no. Diesel operated motor cab (Car No.- WB25K-2915) with driver for official use for Assistant Engineer (HQ-II), Barasat Arsenic Division, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil w.e.f. 01.05.2023 to 16.11.2023. | Assistant Engineer, Barasat Arsenic Sub-Division,Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000025/2023-2024 | 1007/B.Ar.D | 26/04/2023 | 12/11/2023 | PREMANANDA ROY BISWAS | 0.95 | 2.58 | 271.47 | 40
14 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11558 | Augmentation | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab (Car No.- WB-25K-2915) with driver for official use for Assistant Engineer (HQ - II), under Barasat Arsenic Division, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil w.e.f. 17.11.2023 to 30.11.2023". | Assistant Engineer, HQ-I, Barasat Arsenic Division,Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000178/2023-2024 | 2660/B.Ar.D | 09/11/2023 | 23/11/2023 | PREMANANDA ROY BISWAS | 0.07 | 0.19 | 279.95 | 0
15 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11558 | Augmentation | Construction of 01 (one) no. pump house (4.88 X 3.66 mtr.) at the site Nababpur of Baghband Saiberia W/S Scheme at Barasat-II block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000157/2023-2024 | 2488/B.Ar.D. | 11/10/2023 | 25/11/2023 | AT CONSTRUCTION | 7.51 | 6.69 | 89.08 | 50
16 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11558 | Augmentation | Construction of 01 (one) no. pump house (4.88 X 3.66 mtr.) at the site Kayemba of Baghband Saiberia W/S Scheme at Barasat-II block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000147/2023-2024 | 2354/B.Ar.D. | 22/09/2023 | 06/11/2023 | SUJAN KUMAR MISTRI | 5.97 | 5.39 | 90.17 | 80
17 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11558 | Augmentation | Laying of Pipeine for Pump Connection with necessarey inter connection arrangement for Two (02) nos Pump House at Kayemba and Nababpur at Baghband Saiberia Water Supply Scheme under Barasat-II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000046/2024-2025 | 1581/B.Ar.D. | 23/09/2024 | 23/10/2024 | SAHA ENTERPRISE | 13.53 | 13.51 | 99.82 | 100
18 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11558 | Augmentation | Payment of quotation amount for new service connection at P/H No: IV , Nababpur under Bagband Saiberia scheme. |  |  | BILL/04806/2023-2024 | BP-302-23-24 | 04/03/2024 | 04/03/2024 | W.B.S.E.D.C.L. (GANGANAGAR C.C.C.) | 7.47 | 0 | 0 | 0
19 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11558 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I/ II (Replacement) and III and IV (New) under Bagband-Saiberia W/S Scheme District of 24 Pgs. (N). | Assistant Engineer | Junior Engineer | ORD/001274/2023-2024 | 4937/EMD | 18/08/2023 | 17/09/2023 | GOENKA ENTERPRISE | 33.23 | 20.32 | 61.13 | 66
20 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11558 | Augmentation | Hiring of one (1) no. Diesel / Petrol operated motor cab (Car No.- WB-25J-3845) with driver for official use for Superintending Engineer, PIU, North 24 Pgs., WBDWSIP, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel / Petrol, Mobil oil w.e.f. 01.07.2024 to 31.12.2024. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000030/2024-2025 | 1051/B.Ar.D | 28/06/2024 | 29/12/2024 | OM ENTERPRISE | 0.87 | 2.2 | 252.17 | 0
21 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | SM/11558 | Augmentation | Restoration of damaged existing pipeline and Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within leftout zone of Krisnamati, Bagberia, Kayemba, Andulia and Kirtipur area for Augmentation of Ground Based Water Supply Scheme at Baghband Saiberia under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000137/2024-2025 | 234/B.Ar.D | 06/02/2025 | 18/12/2025 | N. H. ENTERPRISE | 34.02 | 0 | 0 | 50
Total | [13 empty] | 644.44 | 357.31 | 55.44