## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11559 | Augmentation | Preparation of Augmentation DPR for Mahisgadi Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000116/2022-2023 | 1952/B.Ar.D | 26/09/2022 | 16/10/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.99 | 0.99 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11559 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2022-2023 | 2297/B.Ar.D | 02/12/2022 | 02/12/2022 | Resource Division | 0.37 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11559 | Augmentation | Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Mahisgadi & its adjoining mouza Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000090/2022-2023 | 1559/B.Ar.D. | 24/08/2022 | 22/11/2022 | M/S R. M. CONSTRUCTION | 131.17 | 112.15 | 85.49 | 85
4 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11559 | Augmentation | Withdrawling and re laying of 250 mm dia upvc pipeline related to the work "Providing Functional House Hold Tap Connection (FHTC) from the existing and new proposed distribution system within Command area at Mahisgadi & its adjoining mouza water supply Scheme under Barasat-II Block Under Barasat Arsenic, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000145/2023-2024 | 2339/B.Ar.D. | 21/09/2023 | 21/10/2023 | M/S R. M. CONSTRUCTION | 6.45 | 6.41 | 99.4 | 95
5 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11559 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2022-2023 | 2107/B.Ar.D. | 02/11/2022 | 02/11/2022 | Resource Division | 0.79 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11559 | Augmentation | Increse of Water pressure through by pass Pipeline from Second tubewell to main distribution pipeline and dedicated pipeline for I.E.P. to haroa khal in Mahisgadi Water Supply Scheme under Barasat Arsenic Division, P.H.E Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000008/2024-2025 | 982/B.Ar.D. | 18/06/2024 | 28/07/2024 | SUJAN KUMAR MISTRI | 4.08 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11559 | Augmentation | Laying of pipeline at damaged portion due to construction of road, drain by panchayet related to the work "Providing Functional House Hold Tap Connection (FHTC) from the existing and new proposed distribution system within Command area at Mahisgadi & its adjoining mouza water supply Scheme under Barasat-II Block Under Barasat Arsenic, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000069/2023-2024 | 1827/B.Ar.D. | 01/08/2023 | 15/09/2023 | P. & S. ASSOCIATES | 28.23 | 27.73 | 98.24 | 100
8 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11559 | Augmentation | Repair and Renovation works of 350 Cum OHR and allied water supply component infrastructure under Mahisgadi W/S Scheme of Barasat -II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000197/2023-2024 | 3027/B.Ar.D. | 29/12/2023 | 12/02/2024 | UMA CONSTRUCTION | 19.75 | 19.6 | 99.22 | 100
9 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11559 | Augmentation | Hiring of one (1) no. Diesel / Petrol operated motor cab (Car No. - WB19J - 2141) with driver for official use for Assistant Engineer (HQ-I), Barasat Arsenic Division, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel / Petrol, Mobil oil w.e.f. 01.07.2024 to 31.12.2024. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000036/2024-2025 | 1023/B.Ar.D | 21/06/2024 | 22/12/2024 | OM ENTERPRISE | 0.87 | 2.23 | 255.38 | 0
10 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11559 | Augmentation | Repairing of damaged diifferent dia pipeline for increasing the functionality of House hold tap connection within command area of Kamuduni Mouza at Mahisgadi W/S Scheme at Barasat-II Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000169/2024-2025 | 430/B.Ar.D. | 10/03/2025 | 09/04/2025 | SANTU GHOSH | 4.83 | 0 | 0 | 100
11 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11559 | Augmentation | Repairing of D.I distribution pipeline in the H/W Site of Mahisgadi Water Supply Scheme under Barasat Arsenic Division, P.H.E Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000178/2024-2025 | 431/B.Ar.D. | 10/03/2025 | 09/04/2025 | SAFE STEP ENTERPRISE | 3.41 | 0 | 0 | 100
12 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11559 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21540.71 | 169.11 | 0.79