## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11659 | Augmentation | Preparation of Augmentation DPR for Tildanga Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000105/2022-2023 | 1833/B.Ar.D | 19/09/2022 | 09/10/2022 | SIRCON ENGINEERING SERVICES | 0.98 | 0.98 | 99.84 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11659 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2022-2023 | 2294/B.Ar.D | 02/12/2022 | 02/12/2022 | Resource Division | 9.3 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11659 | Augmentation | Sinking for 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method near Pump House no.-2 with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter at Tildanga w/s scheme of Baduria block under Barasat Arsenic Division, P.H.E. Dte. (Sl No. 4) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000134/2022-2023 | 2058/B.Ar.D. | 19/10/2022 | 03/12/2022 | TRISHA ENTERPRISE AND CO. | 15.35 | 13.35 | 86.92 | 1
4 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11659 | Augmentation | Repair and Renovation works of OHR and allied water supply component infrastructure under Tildanga W/S Scheme of Baduria Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000023/2023-2024 | 949/B.Ar.D. | 17/04/2023 | 16/06/2023 | MONDAL ENTERPRISE | 12.55 | 12.07 | 96.22 | 100
5 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11659 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2022-2023 | 2113/B.Ar.D. | 02/11/2022 | 02/11/2022 | Resource Division | 9.89 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11659 | Augmentation | New service connection at PH-III under Tildanga W/S Scheme. |  |  | BILL/01904/2023-2024 | BP-124-23-24 | 07/08/2023 | 07/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.17 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11659 | Augmentation | Laying of distribution System Including specials all Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Tildanga at Baduria Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000099/2022-2023 | 1572/B.Ar.D. | 25/08/2022 | 10/02/2025 | AMIT KUMAR BOSE | 249.41 | 168.27 | 67.47 | 81
8 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11659 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Rep.) under Tildanga W/S Scheme District of 24 Pgs. (N) NIET No.- 27 of EE/EMD of 2022-23 (Sl. No.- 38) | Assistant Engineer | Junior Engineer | ORD/000002/2023-2024 | 1439/EMD | 10/04/2023 | 10/05/2023 | C.M ENTERPRISE | 21.22 | 13.6 | 64.08 | 60
9 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11659 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at P.H. No.-III under Tildanga ground water based w/s scheme under Block_ Baduria in the District of North 24 Parganas under Eastern Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000208/2024-2025 | 1909/EMD | 31/07/2024 | 30/08/2024 | TAMAL ENTERPRISE | 9.15 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11659 | Augmentation | Laying of UPVC/HDPE pipeline and Repairing , Rennovation of Boundary wall, Fencing work etc and other allied works at Head work site of Tildanga W/S Scheme under Baduria Block under Barasat Arsenic Division PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000230/2023-2024 | 391/B.Ar.D | 21/02/2024 | 06/04/2024 | KUNDU CONSTRUCTION CO. | 12.41 | 12.36 | 99.65 | 100
11 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11659 | Augmentation | Laying of pipe line & inter connection at PH No.-3 for Tildanga water supply scheme under Baduria Block in the district of North 24 Parganas under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000180/2024-2025 | 433/B.Ar.D. | 10/03/2025 | 09/04/2025 | CHOWDHURY CONSTRUCTION | 4.68 | 0 | 0 | 0
12 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11659 | Augmentation | Replacement of 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method at Pump House no.-2 with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter at Tildanga w/s scheme of Baduria block under Barasat Arsenic Division, P.H.E. Dte. (SM/11659) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000005/2025-2026 | 797/B.Ar.D. | 30/04/2025 | 12/09/2025 | MONDAL & CO | 15.49 | 0 | 0 | 100
Total | [13 empty] | 364.59 | 220.63 | 60.52