## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KONANAGAR to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte | SM/11661 | Augmentation | Preparation of Augmentation DPR for Konanagar Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000109/2022-2023 | 1837/B.Ar.D | 19/09/2022 | 09/10/2022 | SIRCON ENGINEERING SERVICES | 0.99 | 0.98 | 99.21 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KONANAGAR to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte | SM/11661 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2022-2023 | 2210/B.Ar.D. | 22/11/2022 | 22/11/2022 | Resource Division | 6.92 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KONANAGAR to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte | SM/11661 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2022-2023 | 2296/B.Ar.D | 02/12/2022 | 02/12/2022 | Resource Division | 10.09 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KONANAGAR to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte | SM/11661 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep) under Hasnabad W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001132/2023-2024 | 4724/EMD | 04/08/2023 | 03/09/2023 | P.K. ENGINEERING | 26.5 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KONANAGAR to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte | SM/11661 | Augmentation | Repair and Renovation works of Existing R.C.C. Elevated Reservoir of Capacity 250 Cu.m. at Konanagar W/S Scheme of Hasnababad Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000193/2022-2023 | 375/B.Ar.D. | 17/02/2023 | 18/04/2023 | NIKHIL SAMADDAR | 13.23 | 12.98 | 98.12 | 0
6 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KONANAGAR to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte | SM/11661 | Augmentation | Laying of distribution System Including specials all Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Konanagar at Hasnabad Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000098/2022-2023 | 1571/B.Ar.D. | 25/08/2022 | 12/11/2024 | M/S R. K. ENTERPRISE | 190.29 | 157.32 | 82.67 | 70
7 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KONANAGAR to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte | SM/11661 | Augmentation | Hiring of one (1) no. Diesel operated motor cab (Car No. WB 07J - 1216) with driver for official use of Assistant Engineer (Sub-Division), Barasat Arsenic Sub ¿ Division under B.Ar.D, PHE Dte. for different works under JJM Schemes with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil w.e.f. 01.03.2024 to 29.08.2024. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000243/2023-2024 | 430/B.Ar.D | 28/02/2024 | 28/08/2024 | OM ENTERPRISE | 0.86 | 2.11 | 244.37 | 0
8 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KONANAGAR to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte | SM/11661 | Augmentation | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab (Car No. WB07J - 1216) with driver for official use of Assistant Engineer (Sub-Division), Barasat Arsenic Sub Division under B.Ar.D, PHE Dte. for different works under JJM Schemes with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil w.e.f. 30.08.2024 to 31.10.2024". | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000119/2024-2025 | 1414/B.Ar.D | 29/08/2024 | 31/10/2024 | OM ENTERPRISE | 0.3 | 0.67 | 224.68 | 0
9 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KONANAGAR to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte | SM/11661 | Augmentation | Hiring of one (1) no. Diesel / Petrol operated motor cab (Car No. WB05 - 2594) with driver for official use for Superintending Engineer, PIU, North 24 Pgs., WBDWSIP, PHE Dte. w.e.f. 01.01.2025 to 30.06.2025. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000217/2024-2025 | 2123/B.Ar.D | 20/12/2024 | 19/06/2025 | SANGJOG | 0.86 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KONANAGAR to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte | SM/11661 | Augmentation | CONTINUATION ORDER for "Hiring of one (1) no. Diesel / Petrol operated motor cab (Car No.- WB05 2594) with driver for official use for Deputy Superintending Engineer, PIU, North 24 Pgs., WBDWSIP, PHE Dte. w.e.f. 01.07.2025 to 30.11.2025". | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000044/2025-2026 | 1102/B.Ar.D | 23/06/2025 | 23/11/2025 | SANGJOG | 0.73 | 0 | 0 | 0
Total | [13 empty] | 250.77 | 174.06 | 69.41