## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11662 | Augmentation | Laying of UPVC Pipe at damaged portion from npde 33-34, 33a-33,44a-47-470 of Jeliakhali Paschim Khanda W/S scheme of Sandeshkhali Block II for providing FHTC under Jalaswapna Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000143/2021-2022 | 2253/B.Ar.D. | 30/12/2021 | 13/02/2022 | BALAJEE ENTERPRISES | 28.09 | 28.09 | 99.98 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11662 | Augmentation | Laying of distribution System, Laying of Rising Main including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at JELIAKHALI PASCHIM KHANDA under Sandeshkhali - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000097/2022-2023 | 1569/B.Ar.D. | 25/08/2022 | 09/02/2025 | PIKASU BOSE | 193.42 | 155.74 | 80.52 | 95
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11662 | Augmentation | Preparation of Augmentation DPR for Jeliakhali Paschim Khanda Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000111/2022-2023 | 1840/B.Ar.D | 19/09/2022 | 09/10/2022 | RISHAN ENGINEERING CONSULTANCY | 0.98 | 0.98 | 99.68 | 1
4 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11662 | Augmentation | Repair and Renovation works of Existing R.C.C. Elevated Reservoir & other existing civil component of Capacity 250 Cu.m. at Jeliakhali Paschim Khanda W/S Scheme under Sandeshkhali-II Block under Barasat Arsenic Division, PHE Dte. (SM/11662) | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000159/2022-2023 | 2471/B.Ar.D. | 21/12/2022 | 19/02/2023 | MAHALAXMI CONSTRUCTION | 15.65 | 14.36 | 91.78 | 1
5 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11662 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2022-2023 | 2109/B.Ar.D. | 02/11/2022 | 02/11/2022 | Resource Division | 2.41 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11662 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2022-2023 | 2289/B.Ar.D | 02/12/2022 | 02/12/2022 | Resource Division | 10.97 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11662 | Augmentation | Repair & Renovation of Iron Elementation Plant of 58 M3 including Media Change of Jeliakhali Paschim Khanda Water Supply Scheme under Sandeshkhali-II Block Under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000211/2022-2023 | 476/B.Ar.D. | 27/02/2023 | 29/03/2023 | IDEAL CONSTRUCTION | 4.83 | 4.53 | 93.85 | 100
8 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11662 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
9 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11662 | Augmentation | Bullah piling for protection of UPVC distribution pipe line at Jeliakhali Paschim Khanda 3 no Para of Jeliakhali Paschim Khanda W/S Scheme under Sandeshkhali- II Block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000028/2023-2024 | 1167/B.Ar.D. | 16/05/2023 | 15/06/2023 | ABDUL ALIM MONDAL | 7.52 | 7.43 | 98.92 | 100
10 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11662 | Augmentation | Supply, delivery and installation of submersible pump moter set including other allied works at P H No. I & II of Jeliakhali Purbakhand water supply scheme under Eastern Mechanical Sub Division-I, PHE Dte. Dist- 24 Pgs(N) |  | Junior Engineer | ORD/000102/2023-2024 | 1501/EMSD-I | 21/06/2023 | 06/07/2023 | M/S DILIP MITRA | 3.19 | 3 | 94.11 | 100
11 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11662 | Augmentation | Laying of distribution System including specials all complete at Pipre khali, 52 Para, Jeliakhali 6 no, adibashi Para for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at JELIAKHALI PASCHIM KHANDA under Sandeshkhali - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000008/2023-2024 | 919/B.Ar.D. | 11/04/2023 | 26/05/2023 | TRISHA ENTERPRISE AND CO. | 44.17 | 44.02 | 99.66 | 95
12 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11662 | Augmentation | Bullah piling for Protection of UPVC distribution pipe line at Jeliakhali Paschim Khanda Jhil para of Jeliakhali Paschim khanda W/S Scheme under Sandeshkhali- II Block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000202/2022-2023 | 474/B.Ar.D. | 27/02/2023 | 24/03/2023 | CHAKRABORTY SUPPLIERS & CONSTRUCTION | 9.87 | 9.85 | 99.79 | 1
13 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11662 | Augmentation | Hiring of one (1) no. Diesel / Petrol operated motor cab ( Car No.- WB25M 3675) with driver for official use of Assistant Engineer (HQ-I) & Assistant Engineer (HQ-II), B.Ar.D, PHE Dte. for different works under JJM Schemes with all costs towards the owner except fuel cost i.e. Diesel / Petrol, Mobil oil w.e.f. 14.08.2024 to 28.02.2025. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000042/2024-2025 | 1330/B.Ar.D | 14/08/2024 | 01/03/2025 | SUSMITA MANDAL | 0.95 | 2.35 | 248.22 | 0
14 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11662 | Augmentation | Laying of Pipeine for Pump Connection and Construction of 4.88 mtr. x 3.60 mtr. size new Pump House with at Jekiakhali Paschimkhanda Water Supply Scheme under Sandeshkhali-II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000044/2024-2025 | 1850/B.Ar.D. | 21/11/2024 | 05/01/2025 | AMIT KUMAR BOSE | 10.45 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11662 | Augmentation | Hiring of one (1) no. Diesel / Petrol operated motor cab (Car No. - WB23F - 6448) with driver for official use for Executive Engineer, Barasat Arsenic Division, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel / Petrol, Mobil oil w.e.f. 01.07.2024 to 31.12.2024. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000035/2024-2025 | 1022/B.Ar.D | 21/06/2024 | 22/12/2024 | RANJIT KUMAR MANDAL | 0.87 | 2.22 | 253.47 | 0
16 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11662 | Augmentation | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab (Car No. WB23F - 6448) with driver for official use for Executive Engineer, Barasat Arsenic Division PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel / Petrol, Mobil oil w.e.f. 01.01.2025 to 28.02.2025. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000134/2024-2025 | 2050/B.Ar.D | 30/12/2024 | 27/02/2025 | RANJIT KUMAR MANDAL | 0.28 | 0.72 | 255.92 | 0
17 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11662 | Augmentation | Sal-Bullah Pilling for pipe protection work at Jeliakhali Paschim Khanda under Sandeshkhali-II Block Under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000012/2024-2025 | 992/B.Ar.D. | 19/06/2024 | 03/08/2024 | OM ENTERPRISE | 14.47 | 14.44 | 99.77 | 100
18 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11662 | Augmentation | Continuation Order for "Hiring of Power Driven Mini Launch of office of the Executive Engineer, Barasat Arsenic Division, P.H.E. Dte." for the period of 91 days (i.e. from 01.04.2024 to 30.06.2024)''. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000256/2023-2024 | 679/B.Ar.D | 28/03/2024 | 27/06/2024 | RANJIT KUMAR MANDAL | 1.04 | 1.76 | 168.74 | 100
Total | [13 empty] | 21688.93 | 289.48 | 1.33