## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11705 | Augmentation | Sinking of 1 no 250 mm. X 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter for Augmentation at 2nd T/W site of Atapur w/s scheme of Sandeshkhali- II block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000007/2022-2023 | 849/B.Ar.D. | 06/05/2022 | 20/06/2022 | M/S. S. S. ENTERPRISE | 19.74 | 15.2 | 77 | 1
2 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11705 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2022-2023 | 2288/B.Ar.D | 02/12/2022 |  | Resource Division | 10.97 | 0 | 0 | 0
3 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11705 | Augmentation | Preparation of Augmentation DPR for Atapur Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000110/2022-2023 | 1839/B.Ar.D | 19/09/2022 | 09/10/2022 | SIRCON ENGINEERING SERVICES | 0.98 | 0.98 | 100 | 1
4 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11705 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II under Atapur W/S Scheme, District of 24 Pgs. (N). (SM/11705) |  |  | ORD/001730/2022-2023 | 6381 /EMD | 24/11/2022 | 24/12/2022 | D.K. ELECTRIC | 10.12 | 0 | 0 | 1
5 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11705 | Augmentation | Sinking of 1 no Replacement 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 250 mm dia 42 mtr. long housing pipe & 150 mm dia 30 mtr. long filter for Augmentation of Atapur w/s Scheme at PH-I of Sandeshkhali-II block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000200/2022-2023 | 467/B.Ar.D. | 27/02/2023 | 13/04/2023 | UNIFIED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 19.81 | 16.64 | 84.01 | 1
6 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11705 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Replacement) under Atapur W/S Scheme, District of 24 Pgs. (N). (SM/11705) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 03) |  |  | ORD/000552/2022-2023 | 6381/EMD | 24/11/2022 | 24/12/2022 | D.K. ELECTRIC | 10.12 | 10.12 | 100 | 0
7 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11705 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2022-2023 | 2112/B.Ar.D. | 02/11/2022 |  | Resource Division | 3.53 | 0 | 0 | 0
8 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11705 | Augmentation | Withdrawing and relaying of pipelines and Sal-Bullah Pilling for pipe protection work at Atapur under Sandeshkhali-II Block Under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000010/2024-2025 | 984/B.Ar.D. | 18/06/2024 | 18/07/2024 | DEL DELTA CONSTRUCTION | 5.88 | 2.89 | 49.14 | 0
9 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11705 | Augmentation | Laying of distribution System, Laying of Rising Main including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at ATAPUR under Sandeshkhali - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000094/2022-2023 | 1567/B.Ar.D. | 25/08/2022 | 23/11/2022 | M/S NIRMAN CONSTRUCTION | 192.73 | 170.34 | 88.38 | 90
10 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11705 | Augmentation | Repair and Renovation of 136 Cum capacity OHR, Construction of 2nd Pump House Boundary Wall at OHR Site, 1st pump house & 2nd pump house pump connection and allied work for Atapur W/S Scheme Under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000198/2023-2024 | 3028/B.Ar.D. | 29/12/2023 | 17/02/2024 | M/S NIRMAN CONSTRUCTION | 73.1 | 36.24 | 49.58 | 55
11 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11705 | Augmentation | Hiring of one (1) no. Diesel / Petrol operated motor cab (Car No. - WB07J - 8656) with driver for official use for Deputy Superintending Engineer, PIU, North 24 Pgs., WBDWSIP, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel / Petrol, Mobil oil w.e.f. 01.07.2024 to 31.12.2024. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000034/2024-2025 | 1021/B.Ar.D | 21/06/2024 | 22/12/2024 | PROBIR SHAW | 0.87 | 0.84 | 95.72 | 0
Total | [13 empty] | 347.88 | 253.26 | 72.8