## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11706 | Augmentation | Preparation of Augmentation DPR for Krishnapara Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000108/2022-2023 | 1836/B.Ar.D | 19/09/2022 | 09/10/2022 | SIRCON ENGINEERING SERVICES | 0.98 | 0.98 | 99.43 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11706 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2022-2023 | 2295/B.Ar.D | 02/12/2022 | 02/12/2022 | Resource Division | 7.71 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11706 | Augmentation | Repair and Renovation works of Existing R.C.C. Elevated Reservoir of Capacity 250 Cu.m. at Krishnapara W/S Scheme of Hasnababad Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000194/2022-2023 | 275/B.Ar.D. | 06/02/2023 | 07/04/2023 | M/S SANJAY ADHIKARI | 13.9 | 13.58 | 97.66 | 0
4 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11706 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 2108/B.Ar.D. | 02/11/2022 | 02/11/2022 | Resource Division | 1.07 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11706 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. II (Rep.) under Krishnapara W/S Scheme District of 24 Pgs. (N). N.I.E.T No. 27 of EE / EMD of 2022-2023 (2022_PHED_431015_27) |  |  | ORD/001886/2023-2024 | 6730/EMD | 28/11/2023 | 28/12/2023 | ASHUTOSH DAS & CO. | 9.82 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11706 | Augmentation | Laying of distribution System Including specials all Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Krishnapara at Hasnabad Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000089/2022-2023 | 1558/B.Ar.D. | 24/08/2022 | 22/11/2022 | PALCON | 103.23 | 69.93 | 67.74 | 100
7 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11706 | Augmentation | Construction of Remaining portion of boundary wall & allied works at Krishnapara Head Work site at Krishnapara Water Supply scheme of Hasnabad Block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000172/2023-2024 | 2657/B.Ar.D. | 09/11/2023 | 24/12/2023 | M/S DAS & CO | 8.62 | 8.56 | 99.33 | 100
8 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11706 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
9 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11706 | Augmentation | Repair & Renovation of I.E.Plant (Capacity-38 Cu.m.) for Augmentation of Krishnapara Water Supply Scheme under Hasnabad Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000213/2024-2025 | 578/B.Ar.D. | 24/03/2025 | 08/05/2025 | SUNIL DULE | 3.77 | 0 | 0 | 80
10 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11706 | Augmentation | Hiring of one (1) no. Diesel / Petrol operated motor cab ( Car No. WB25M 3675) with driver for official use for Executive Engineer, Barasat Arsenic Division, PHE Dte. w.e.f. 01.03.2025 to 28.08.2025. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000148/2024-2025 | 328/B.Ar.D | 27/02/2025 | 27/08/2025 | SUSMITA MANDAL | 0.86 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11706 | Augmentation | Laying and Refixing of Ferrule of distribution Pipeline for Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area of Krishnapara W/S Scheme at Hasnabad Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. (SM/11706) | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000003/2025-2026 | 795/B.Ar.D. | 30/04/2025 | 14/06/2025 | BABUSONA CONSTRUCTION | 37.18 | 0 | 0 | 0
12 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11706 | Augmentation | CONTINUATION ORDER for " Hiring of one (1) no. Diesel / Petrol operated motor cab (Car No. WB25M 3675) with driver for official use for Executive Engineer, Barasat Arsenic Division, PHE Dte. w.e.f. 29.08.2025 to 31.01.2026". | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000065/2025-2026 | 1463/B.Ar.D | 25/08/2025 | 28/01/2026 | SUSMITA MANDAL | 0.74 | 0 | 0 | 0
Total | [13 empty] | 21527.65 | 93.05 | 0.43