## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11707 | Augmentation | Laying of distribution System, Laying of Rising Main including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at DWARIR JANGLE under Sandeshkhali - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000096/2022-2023 | 1568/B.Ar.D. | 25/08/2022 | 23/11/2022 | M/S DIPAK ENTERPRISE | 227.76 | 171.75 | 75.41 | 92
2 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11707 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No-I/II (Rep.) under Dwarir Jangle W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001168/2023-2024 | 4796/EMD | 09/08/2023 | 08/09/2023 | P.K. ENGINEERING | 11.63 | 0 | 0 | 0
3 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11707 | Augmentation | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab ( Car No. WB-07J-8656) with driver for official use for Deputy Superintending Engineer, PIU, North 24 Pgs., WBDWSIP, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 17.01.2024 to 31.05.2024". | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000209/2023-2024 | 85/B.Ar.D | 11/01/2024 | 26/05/2024 | PROBIR SHAW | 0.65 | 0 | 0 | 70
4 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11707 | Augmentation | Laying of Pipeline and Repairing of House Hold Connection and Allied works at Dwarir Jangle Water Supply Scheme under Barasat Arsenic Division PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000049/2024-2025 | 1523/B.Ar.D. | 12/09/2024 | 22/10/2024 | MONDAL ENTERPRISE | 13.09 | 0 | 0 | 40
5 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11707 | Augmentation | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab ( Car No. WB-07J-8656) with driver for official use for Deputy Superintending Engineer, PIU, North 24 Pgs., WBDWSIP, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 01.06.2024 to 30.06.2024". | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000020/2024-2025 | 919/B.Ar.D | 30/05/2024 | 29/06/2024 | PROBIR SHAW | 0.14 | 0 | 0 | 0
6 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11707 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. II under Chowlpur W/S Scheme and Pump House No-III (New) under Dwarir Jangle W/S Scheme District of 24 Pgs. (N) | Assistant Engineer |  | ORD/003349/2023-2024 | 4805/EMD | 09/08/2023 | 08/09/2023 | P.K. ENGINEERING | 21.79 | 0 | 0 | 0
7 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11707 | Augmentation | Repair and Renovation works of Existing R.C.C. Elevated Reservoir & other existing civil component of Capacity 250 Cu.m. at Dwarir Jungle W/S Scheme uder Sandeshkhali-II Block under Barasat Arsenic Division, PHE Dte. (SM/11707) | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000158/2022-2023 | 2470/B.Ar.D. | 21/12/2022 | 19/02/2023 | MONDAL ENTERPRISE | 16.13 | 15.35 | 95.12 | 1
8 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11707 | Augmentation | Preparation of Augmentation DPR for Dwarir Jangle Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000112/2022-2023 | 1841/B.Ar.D | 19/09/2022 | 09/10/2022 | RISHAN ENGINEERING CONSULTANCY | 0.99 | 0.98 | 99.68 | 1
9 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11707 | Augmentation | Construction of Platform for FHTC works at Dwarir Jungle Ground Water Supply Scheme under Sandeshkhali-II Block under "Jal Jiban Mission" programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division,Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000198/2022-2023 | 311/B.Ar.D. | 09/02/2023 | 11/03/2023 | MONDAL ENTERPRISE | 2.97 | 2.97 | 100 | 100
10 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11707 | Augmentation | Construction of Boundary Wall & Repairing of Pump House-II and approach road with allied work at PH-II for DWARIR JANGLE W/S Scheme Under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000207/2022-2023 | 471/B.Ar.D. | 27/02/2023 | 13/04/2023 | M/S ROY CHOWDHURY & CO. | 13.15 | 12.88 | 97.97 | 100
11 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11707 | Augmentation | Laying of distribution System including specials all complete at Naskar Para, 3 no Para, 9 No Katkhali Para for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at DWARIR JANGLE under Sandeshkhali - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000001/2023-2024 | 918/B.Ar.D. | 11/04/2023 | 26/05/2023 | M/S DATTA ENTERPRISE | 46.93 | 28.73 | 61.22 | 100
12 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11707 | Augmentation | Construction of Boundary Wall & Repairing of Pump House-I, IEP Room and approach road with allied work of Head Work Site for DWARIR JANGLE W/S Scheme Under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000007/2023-2024 | 917/B.Ar.D. | 11/04/2023 | 26/05/2023 | M/S. PROGATI ENTERPRISE | 28.62 | 26.88 | 93.94 | 100
13 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11707 | Augmentation | Eucalyptus - Bullah pilling for Protection of UPVC distribution pipe line at Sardarpara of Dwarir Jangle W/S Scheme under Sandeshkhali- II Block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000031/2023-2024 | 1166/B.Ar.D. | 16/05/2023 | 06/06/2023 | R. K. MANDAL & CO. | 4.79 | 0 | 0 | 100
14 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11707 | Augmentation | Hiring of one (1) no. Diesel operated motor cab (Car No. WB-07J-8656) with driver for official use for Deputy Superintending Engineer, PIU, North 24 Pgs., WBDWSIP, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 01.07.2023 to 16.01.2024. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000047/2023-2024 | 1472/B.Ar.D | 26/06/2023 | 12/01/2024 | PROBIR SHAW | 0.95 | 1.13 | 118.73 | 100
15 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11707 | Augmentation | Continuation Order for "Hiring of Power Driven Mini Launch of office of the Executive Engineer, Barasat Arsenic Division, P.H.E. Dte." for the period of 183 days (i.e. from 01.10.2023 to 31.03.2024)''. |  |  | ORD/000183/2023-2024 | 2397/B.Ar.D | 29/09/2023 | 30/03/2024 | RANJIT KUMAR MANDAL | 2.1 | 0 | 0 | 100
16 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11707 | Augmentation | Laying of Pipe line in place of damage portion of distribution system & Construction of 4.88 mtr. x 3.60 mtr. size new Pump House at 3 No. School Para of Dwarir Jangle Supply Scheme under Sandeshkhali-II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000223/2023-2024 | 387/B.Ar.D. | 21/02/2024 | 21/04/2024 | A 8T CONSTRUCTION | 9.77 | 0 | 0 | 80
17 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11707 | Augmentation | Pipe protection work with Sal- Bullah Pilling and FHTC Strengthening with other allied works at DWARIR JANGLE water supply scheme under Sandeshkhali - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000221/2023-2024 | 385/B.Ar.D. | 21/02/2024 | 22/03/2024 | SUTAPA ENTERPRISE | 14.21 | 0 | 0 | 100
18 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11707 | Augmentation | Sinking of 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method 3 No. School Para with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter for Augmentation of Dwarir Jangle w/s scheme of Sandeshkhali-II block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000222/2023-2024 | 386/B.Ar.D. | 21/02/2024 | 06/04/2024 | M/S RAJPATH CONSTRUCTION | 19.49 | 0 | 0 | 100
19 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11707 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2022-2023 | 2111/B.Ar.D. | 02/11/2022 |  | Resource Division | 4.33 | 0 | 0 | 0
20 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11707 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2022-2023 | 2290/B.ar.D | 02/12/2022 |  | Resource Division | 9.3 | 0 | 0 | 0
Total | [13 empty] | 448.77 | 260.67 | 58.09