## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for RAJAPURA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/13761 | Augmentation | Hiring of one (1) no. Diesel / Petrol operated motor cab (Car No. WB19J 4175) with driver for official use for Superintending Engineer, PIU, North 24 Pgs., WBDWSIP, PHE Dte. w.e.f. 01.01.2025 to 30.06.2025. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000101/2024-2025 | 2068/B.Ar.D. | 16/12/2024 | 15/06/2025 | OM ENTERPRISE | 0.86 | 0 | 0 | 0
2 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for RAJAPURA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/13761 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I , II Zone-I under Rajapura ground water based water supply scheme under Block_ Sandeshkhali-I Dist. - North 24PGS under EMD, PHE Dte. WBPHED/EE/EMD/NIeT-37 of 2023-24 (Sl no. 12) | Assistant Engineer |  | ORD/003196/2023-2024 | 944/EMD | 18/03/2024 | 17/04/2024 | PADMA ENGINEERING CO. | 25.48 | 0 | 0 | 0
3 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for RAJAPURA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/13761 | Augmentation | Laying of distribution System Including specials all Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Rajapura at Hasnabad Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000155/2022-2023 | 2326/BArD | 06/12/2022 | 06/03/2023 | SAKTI ENTERPRISE | 115.75 | 34.4 | 29.72 | 100
4 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for RAJAPURA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/13761 | Augmentation | Repair and Renovation works of Existing R.C.C. Elevated Reservoir of Capacity 250 Cu.m. at Rajapura W/S Scheme of Hasnababad Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000195/2022-2023 | 276/B.Ar.D. | 06/02/2023 | 07/04/2023 | MONDAL ENTERPRISE | 11.21 | 8.61 | 76.84 | 1
5 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for RAJAPURA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/13761 | Augmentation | Preparation of Augmentation DPR for Rajapura Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000024/2023-2024 | 1030/B.Ar.D | 28/04/2023 | 19/05/2023 | SIRCON ENGINEERING SERVICES | 0.98 | 0.98 | 99.84 | 100
6 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for RAJAPURA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/13761 | Augmentation | Laying of distribution system including specials all providing Functional House hold Tap Connection (FHTC) from existing and new proposed distribution system system within command area for Augmentation of Ground Based Water Supply Scheme at Rajapura at Hasnabad Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000048/2023-2024 | 1621/B.Ar.D. | 12/07/2023 | 10/09/2023 | B S ENTERPRISE | 48.59 | 32.09 | 66.06 | 100
7 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for RAJAPURA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/13761 | Augmentation | Sal-Bullah Pilling for pipe protection work at Rajapura under Hasnabad Block Under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000013/2024-2025 | 993/B.Ar.D. | 19/06/2024 | 29/07/2024 | M/S ROY CHOWDHURY & CO. | 14.43 | 0 | 0 | 100
8 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for RAJAPURA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/13761 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2022-2023 | 27/B.Ar.D. | 05/01/2023 |  | Resource Division | 1.72 | 0 | 0 | 0
Total | [13 empty] | 219.03 | 76.09 | 34.74