## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Thakdari Piped Water Supply Scheme in Rajarhat Block of North 24 Parganas District under Barasat Arsenic Division, P.H.E. Dte. | SM/15559 | Augmentation | Sinking of 300 mm. x 200 mm. dia. x 330 mtr. deep tube well by direct rotary rig method for 3rd Tubewell at Thakdari of Zone - V, near Thakdari Head Work site under SWBPWSS under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000022/2022-2023 | 1000/B.Ar.D. | 02/06/2022 | 17/07/2022 | AUXILIARY TUBEWELL DRILLERS | 21.16 | 14.93 | 70.55 | 100
2 | NORTH 24 PARGANAS |  | NTK Mechanical | Augmentation of Thakdari Piped Water Supply Scheme in Rajarhat Block of North 24 Parganas District under Barasat Arsenic Division, P.H.E. Dte. | SM/15559 | Augmentation | Supply & Installation of pumping machineries & other electro-mechanical accessories in Thakdari piped W/S scheme under New Town Kolkata Mechanical Division, P.H.E. Dte. |  |  | ORD/000041/2023-2024 | 783 / NTKMD | 26/05/2023 | 22/11/2023 | DIPALI CONSTRUCTION | 27.24 | 0 | 0 | 85
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Thakdari Piped Water Supply Scheme in Rajarhat Block of North 24 Parganas District under Barasat Arsenic Division, P.H.E. Dte. | SM/15559 | Augmentation | Supplying & laying, fitting, fixing, jointing etc. of different dia HDPE pipe line for distribution system and Laying of Rising Main from existing H/W Site to OHR Site and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN6) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete for Thakdari Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000061/2023-2024 | 1775/B.Ar.D. | 27/07/2023 | 27/07/2024 | SAHA ENTERPRISE | 123.54 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Thakdari Piped Water Supply Scheme in Rajarhat Block of North 24 Parganas District under Barasat Arsenic Division, P.H.E. Dte. | SM/15559 | Augmentation | Construction of Boundary Wall at Thakdari OHR site under SWBPWSS for arsenic affected areas of Haroa, Rajarhat & Bhangar-II Block under Barasat Arsenic Division. PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000188/2023-2024 | 2941/B.Ar.D. | 22/12/2023 | 01/03/2024 | AZAD CONSTRUCTION | 20.36 | 15.77 | 77.45 | 85
5 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Thakdari Piped Water Supply Scheme in Rajarhat Block of North 24 Parganas District under Barasat Arsenic Division, P.H.E. Dte. | SM/15559 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme Thakdari under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000141/2023-2024 | 2334/B.Ar.D. | 21/09/2023 | 12/10/2023 | UMWELT ENGINEER PVT. LTD. | 3.23 | 3.23 | 100 | 100
6 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Thakdari Piped Water Supply Scheme in Rajarhat Block of North 24 Parganas District under Barasat Arsenic Division, P.H.E. Dte. | SM/15559 | Augmentation | Supply, delivery, installation & commissioning of 200 mm Dia Electromagnetic Flowmeter, RTU, Sluice valve etc. and other allied works at Thakdari water supply Scheme under Rajarhat Block under SWBPWSS in Rajarhat, Haroa & Bhangar II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000123/2023-2024 | 1936/B.Ar.D. | 14/08/2023 | 06/08/2025 | MSA INSTRUMENTS | 6.43 | 5.1 | 79.31 | 80
7 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Thakdari Piped Water Supply Scheme in Rajarhat Block of North 24 Parganas District under Barasat Arsenic Division, P.H.E. Dte. | SM/15559 | Augmentation | Construction of 1 (one) no. (G+1 Storied) switch room cum chlorine room and Scada Room (4.1m x 5.9m) including sanitary arrangement the site of Thakdari W/S scheme under Barasat Arsenic Division. PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000056/2024-2025 | 1875/B.Ar.D. | 26/11/2024 | 15/01/2025 | ROY BISWAS CONSTRUCTION | 15.43 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Augmentation of Thakdari Piped Water Supply Scheme in Rajarhat Block of North 24 Parganas District under Barasat Arsenic Division, P.H.E. Dte. | SM/15559 | Augmentation | Connection of Newly constructed OHR at Thakdari and Other Allied Works under Thakdari Water Supply Scheme under Barasat Arsenic Division. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000104/2024-2025 | 79/B.Ar.D | 13/01/2025 | 27/02/2025 | OM ENTERPRISE | 5.37 | 0 | 0 | 100
Total | [13 empty] | 222.77 | 39.04 | 17.52