## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Rajarhat | Barasat Arsenic Division | JATRAGACHHI Piped Water Supply Scheme | SM/16625 | New | Construction of 3.60 mtr. x 3.00 mtr. size new Pump House for at 2nd Tube Well Site of JATRAGACHI Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000051/2023-2024 | 1651/B.Ar.D. | 17/07/2023 | 15/09/2023 | R. UNIQUE CONSTRUCTION | 6.21 | 0 | 0 | 0
2 | NORTH 24 PARGANAS | Rajarhat | Barasat Arsenic Division | JATRAGACHHI Piped Water Supply Scheme | SM/16625 | New | Construction of 5.48 mtr. x 3.60 mtr. size new Pump House at Head Work Site of JATRAGACHI Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000055/2023-2024 | 1661/B.Ar.D. | 18/07/2023 | 16/09/2023 | M.R.H CONSTRUCTION | 7.49 | 0 | 0 | 0
3 | NORTH 24 PARGANAS | Rajarhat | Barasat Arsenic Division | JATRAGACHHI Piped Water Supply Scheme | SM/16625 | New | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at Head Work site of Jatragachhi Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000059/2023-2024 | 1671/B.Ar.D. | 19/07/2023 | 02/09/2023 | SARKAR ENTERPRISE AND CO | 18.23 | 0 | 0 | 0
4 | NORTH 24 PARGANAS | Rajarhat | Barasat Arsenic Division | JATRAGACHHI Piped Water Supply Scheme | SM/16625 | New | Jatragachhi Piped Water Supply Scheme with Rising Main, LDS, FHTC & construction of 350 cum capacity Overhead Reservoir (OHR) including Soil investigation and foundation design at Jatragachhi under Rajarhat block, Dist.- North 24 Parganas. | Assistant Engineer, Barasat Arsenic Sub-Division |  | ORD/000081/2023-2024 | 1841/B.Ar.D. | 02/08/2023 | 02/08/2024 | G. B. CONSTRUCTION AND CO. | 462.81 | 0 | 0 | 0
5 | NORTH 24 PARGANAS | Rajarhat | NTK Mechanical | JATRAGACHHI Piped Water Supply Scheme | SM/16625 | New | Supply & Installation of pumping machineries & other electro-mechanical accessories in Jatragachi piped W/S scheme under New Town Kolkata Mechanical Division, P.H.E. Dte. |  |  | ORD/000223/2023-2024 | 2132/NTKMD | 11/08/2023 | 07/02/2024 | GLACIER ENGINEERING CO. | 43.91 | 0 | 0 | 0
6 | NORTH 24 PARGANAS | Rajarhat | Barasat Arsenic Division | JATRAGACHHI Piped Water Supply Scheme | SM/16625 | New | Survey, Design Drawing & DPR Preparation for NEW PWSS (JATRAGACHHI Water Supply Scheme) in RAJARHAT BLOCK under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000003/2023-2024 | 983/B.Ar.D. | 20/04/2023 | 20/05/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 7.05 | 7.05 | 100 | 100
7 | NORTH 24 PARGANAS | Rajarhat | Barasat Arsenic Division | JATRAGACHHI Piped Water Supply Scheme | SM/16625 | New | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 80/B.Ar.D | 11/01/2024 | 11/01/2024 | Resource Division | 12.65 | 0 | 0 | 0
8 | NORTH 24 PARGANAS | Rajarhat | Barasat Arsenic Division | JATRAGACHHI Piped Water Supply Scheme | SM/16625 | New | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at 2nd Pump House site of Jatragachhi Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000060/2023-2024 | 1672/B.Ar.D. | 19/07/2023 | 02/09/2023 | ANKUSH CONSTRUCTION & CO. | 18.22 | 0 | 0 | 0
Total | [13 empty] | 576.57 | 7.05 | 1.22