## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Barasat-II | Barasat Arsenic Division | BARDASIA Piped Water Supply Scheme | SM/16626 | New | Survey, Design Drawing & DPR Preparation for BARDASIA Water Supply Scheme (NEW PWSS) in BARASAT-II BLOCK under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000002/2023-2024 | 981/B.Ar.D. | 20/04/2023 | 20/05/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 7.16 | 7.16 | 100 | 100
2 | NORTH 24 PARGANAS | Barasat-II | Central Drilling | BARDASIA Piped Water Supply Scheme | SM/16626 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3 | NORTH 24 PARGANAS | Barasat-II | Barasat Arsenic Division | BARDASIA Piped Water Supply Scheme | SM/16626 | New | Laying of Distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from distribution system within command area, Construction of 2 nos pump house and Construction of 400 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir including soil test as per Departmental design, drawing and specification including bored pile & pile cap for BARDASIA Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000091/2023-2024 | 1882/B.Ar.D. | 04/08/2023 | 04/08/2024 | SINGHA ROY AND CO | 430.21 | 0 | 0 | 0
4 | NORTH 24 PARGANAS | Barasat-II | Eastern Mechanical | BARDASIA Piped Water Supply Scheme | SM/16626 | New | Providing And Installation of Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Bardasia Piped Water SupplyScheme, Block: Barasat-II Dist. North 24 Pgs under EMD, PHE Dte. |  |  | ORD/001273/2023-2024 | 4936/EMD | 18/08/2023 | 17/09/2023 | H.K. DAS & CO. | 52.08 | 0 | 0 | 0
5 | NORTH 24 PARGANAS | Barasat-II | Barasat Arsenic Division | BARDASIA Piped Water Supply Scheme | SM/16626 | New | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 62/B.Ar.D | 09/01/2024 | 09/01/2024 | Resource Division | 12.12 | 0 | 0 | 0
Total | [13 empty] | 21841.34 | 7.16 | 0.03