## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Barasat-II | Eastern Mechanical | KOLA Piped Water Supply Scheme | SM/18591 | New | Providing And Installation of Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant (Headworks Site) at Kola Piped Water SupplyScheme, Block: Barasat-II, Dist. North 24 Pgs under EMD, PHE Dte. |  |  | ORD/001266/2023-2024 | 4934/EMD | 18/08/2023 | 17/09/2023 | WESTERN ENGINEERING CO. | 52.69 | 0 | 0 | 0
2 | NORTH 24 PARGANAS | Barasat-II | Barasat Arsenic Division | KOLA Piped Water Supply Scheme | SM/18591 | New | Laying of Distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from distribution system within command area, construction of 2 nos. pump house & construction of 600 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir & soil test as per Departmental design, drawing and specification including bored pile & pile cap at KOLA water supply scheme, Barasat-II block under Barasat Arsenic Division, P.H.E. Dte | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000093/2023-2024 | 1937/B.Ar.D. | 14/08/2023 | 14/08/2024 | MONDAL ENTERPRISE | 639.02 | 0 | 0 | 0
3 | NORTH 24 PARGANAS | Barasat-II | Barasat Arsenic Division | KOLA Piped Water Supply Scheme | SM/18591 | New | Survey, Design Drawing & DPR Preparation for KOLA Water Supply Scheme (NEW PWSS) in BARASAT-II BLOCK under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000124/2023-2024 | 1836/B.Ar.D. | 01/08/2023 | 31/08/2023 | TIYAS CONSULTANCY AND INFRASTRUCTURE PRIVATE LIMITED | 11.36 | 11.36 | 100 | 100
4 | NORTH 24 PARGANAS | Barasat-II | Barasat Arsenic Division | KOLA Piped Water Supply Scheme | SM/18591 | New | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 68/B.Ar.D | 10/01/2024 | 10/01/2024 | Resource Division | 20.22 | 0 | 0 | 0
Total | [13 empty] | 723.29 | 11.36 | 1.57