## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Rajarhat | NTK Mechanical | TARULIA Piped Water Supply Scheme | SM/18598 | New | Supply & Installation of pumping machineries & other electro-mechanical accessories in Tarulia piped W/S scheme under New Town Kolkata Mechanical Division, P.H.E. Dte. |  |  | ORD/000227/2023-2024 | 2134/NTKMD | 11/08/2023 | 07/02/2024 | AHALYA ENGINEERING WORKS | 73.96 | 0 | 0 | 0
2 | NORTH 24 PARGANAS | Rajarhat | Barasat Arsenic Division | TARULIA Piped Water Supply Scheme | SM/18598 | New | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at 3rd Pump House site of Tarulia Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000089/2023-2024 | 1947/B.Ar.D. | 14/08/2023 | 28/09/2023 | ACME CONSTRUCTION | 18.27 | 0 | 0 | 0
3 | NORTH 24 PARGANAS | Rajarhat | Barasat Arsenic Division | TARULIA Piped Water Supply Scheme | SM/18598 | New | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at Head Work site of Tarulia Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000087/2023-2024 | 1945/B.Ar.D. | 14/08/2023 | 28/09/2023 | ACME CONSTRUCTION | 18.27 | 0 | 0 | 0
4 | NORTH 24 PARGANAS | Rajarhat | Barasat Arsenic Division | TARULIA Piped Water Supply Scheme | SM/18598 | New | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at 2nd Pump House site of Tarulia Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000088/2023-2024 | 1946/B.Ar.D. | 14/08/2023 | 28/09/2023 | ACME CONSTRUCTION | 18.27 | 0 | 0 | 0
5 | NORTH 24 PARGANAS | Rajarhat | Barasat Arsenic Division | TARULIA Piped Water Supply Scheme | SM/18598 | New | Construction of 4.88 mtr. x 3.60 mtr. size new Pump House at Head Work Site of TARULIA Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000130/2023-2024 | 1987/B.Ar.D. | 18/08/2023 | 17/10/2023 | M/S DAS & CO | 7.38 | 0 | 0 | 0
6 | NORTH 24 PARGANAS | Rajarhat | Barasat Arsenic Division | TARULIA Piped Water Supply Scheme | SM/18598 | New | Construction of 3.60 mtr. x 3.00 mtr. size new Pump House for at 2nd Tube Well Site of TARULIA Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000131/2023-2024 | 1988/B.Ar.D. | 18/08/2023 | 17/10/2023 | B. S. ENTERPRISE | 6.23 | 0 | 0 | 0
7 | NORTH 24 PARGANAS | Rajarhat | Barasat Arsenic Division | TARULIA Piped Water Supply Scheme | SM/18598 | New | Construction of 3.60 mtr. x 3.00 mtr. size new Pump House for at 3rd Tube Well Site of TARULIA Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000132/2023-2024 | 1989/B.Ar.D. | 18/08/2023 | 17/10/2023 | SHIVAM CONSTRUCTION | 6.18 | 0 | 0 | 0
8 | NORTH 24 PARGANAS | Rajarhat | Barasat Arsenic Division | TARULIA Piped Water Supply Scheme | SM/18598 | New | Tarulia Piped Water Supply Scheme with Rising Main, LDS, FHTC & construction of 600 cum capacity Overhead Reservoir (OHR) including Soil investigation and foundation design at Tarulia under Rajarhat block, Dist.- North 24 Parganas. | Assistant Engineer, Barasat Arsenic Division |  | ORD/000163/2023-2024 | 2557/B.Ar.D. | 30/10/2023 | 30/10/2024 | AZAD ENTERPRISE | 663.57 | 0 | 0 | 0
9 | NORTH 24 PARGANAS | Rajarhat | Barasat Arsenic Division | TARULIA Piped Water Supply Scheme | SM/18598 | New | Survey, Design Drawing & DPR Preparation for NEW PWSS (TARULIA Water Supply Scheme) in RAJARHAT BLOCK under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000126/2023-2024 | 1838/B.Ar.D. | 01/08/2023 | 31/08/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 11.11 | 11.11 | 100 | 100
10 | NORTH 24 PARGANAS | Rajarhat | Barasat Arsenic Division | TARULIA Piped Water Supply Scheme | SM/18598 | New | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 76/B.Ar.D | 11/01/2024 | 11/01/2024 | Resource Division | 26.28 | 0 | 0 | 0
Total | [13 empty] | 849.52 | 11.11 | 1.31