## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Rajarhat | Barasat Arsenic Division | RAIGACHHI Piped Water Supply Scheme. | SM/18599 | New | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at Head Work site of Raigachhi Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000082/2023-2024 | 1940/B.Ar.D. | 14/08/2023 | 28/09/2023 | NEW LIFE CONSTRUCTION | 18.18 | 0 | 0 | 0
2 | NORTH 24 PARGANAS | Rajarhat | Barasat Arsenic Division | RAIGACHHI Piped Water Supply Scheme. | SM/18599 | New | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at 2nd Pump House site of Raigachhi Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000083/2023-2024 | 1941/B.Ar.D. | 14/08/2023 | 28/09/2023 | ABDUL HAMID GAZI | 18.17 | 0 | 0 | 0
3 | NORTH 24 PARGANAS | Rajarhat | NTK Mechanical | RAIGACHHI Piped Water Supply Scheme. | SM/18599 | New | Supply & Installation of pumping machineries & other electro-mechanical accessories in Raigachhi piped W/S scheme under New Town Kolkata Mechanical Division, P.H.E. Dte. |  |  | ORD/000224/2023-2024 | 2131/NTKMD | 11/08/2023 | 07/02/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 47.44 | 0 | 0 | 0
4 | NORTH 24 PARGANAS | Rajarhat | Barasat Arsenic Division | RAIGACHHI Piped Water Supply Scheme. | SM/18599 | New | Construction of 4.88 mtr. x 3.60 mtr. size new Pump House at Head Work Site of RAIGACHI Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000133/2023-2024 | 1990/B.Ar.D. | 18/08/2023 | 17/10/2023 | SAFE STEP ENTERPRISE | 7.29 | 0 | 0 | 0
5 | NORTH 24 PARGANAS | Rajarhat | Barasat Arsenic Division | RAIGACHHI Piped Water Supply Scheme. | SM/18599 | New | Construction of 3.60 mtr. x 3.00 mtr. size new Pump House for at 2nd Tube Well Site of RAIGACHI Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000134/2023-2024 | 1991/B.Ar.D. | 18/08/2023 | 17/10/2023 | B.M.TRADERS | 6.19 | 0 | 0 | 0
6 | NORTH 24 PARGANAS | Rajarhat | Barasat Arsenic Division | RAIGACHHI Piped Water Supply Scheme. | SM/18599 | New | Survey, Design Drawing & DPR Preparation for NEW PWSS (RAIGACHHI Water Supply Scheme) in RAJARHAT BLOCK under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000125/2023-2024 | 1837/B.Ar.D. | 01/08/2023 | 31/08/2023 | TIYAS CONSULTANCY AND INFRASTRUCTURE PRIVATE LIMITED | 7.85 | 0 | 0 | 100
7 | NORTH 24 PARGANAS | Rajarhat | Barasat Arsenic Division | RAIGACHHI Piped Water Supply Scheme. | SM/18599 | New | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 79/B.Ar.D | 11/01/2024 | 11/01/2024 | Resource Division | 12.75 | 0 | 0 | 0
8 | NORTH 24 PARGANAS | Rajarhat | Barasat Arsenic Division | RAIGACHHI Piped Water Supply Scheme. | SM/18599 | New | Raigachhi Piped Water Supply Scheme with Rising Main, LDS, FHTC & construction of 350 cum capacity Overhead Reservoir (OHR) including Soil investigation and foundation design at Raigachhi under Rajarhat block, Dist.- North 24 Parganas. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000094/2023-2024 | 1934/B.Ar.D. | 11/08/2023 | 11/08/2025 | BALAJEE ENTERPRISES | 416.01 | 0 | 0 | 20
Total | [13 empty] | 533.89 | 0 | 0