## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | SURFACE BASED PWSS FOR BARASAT-II BLOCK | SM/19040 | Augmentation | Survey, Design Drawing & DPR Preparation for Surface Based PWSS for Barasat-II Block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000241/2023-2024 | 539/B.Ar.D. | 13/03/2024 | 03/04/2024 | UMWELT ENGINEER PVT. LTD. | 66.14 | 66.14 | 100 | 100
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | SURFACE BASED PWSS FOR BARASAT-II BLOCK | SM/19040 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2023-2024 | 244/B.Ar.D. | 06/02/2024 | 06/02/2024 | Resource Division | 4012.31 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | SURFACE BASED PWSS FOR BARASAT-II BLOCK | SM/19040 | Augmentation | Laying, fitting, fixing, jointing etc of Primary & Secondary Rising Main and Construction of Ground Level Reservoir (GLR) Capacity 1100 CUM with all allied works of Barasat-II Block for Surface Based PWSS for Barasat-II Block in the district of North 24 Parganas under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000211/2023-2024 | 159/B.Ar.D. | 25/01/2024 | 24/01/2026 | SUPRITI ENTERPRISE | 2710.36 | 0 | 0 | 10
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | SURFACE BASED PWSS FOR BARASAT-II BLOCK | SM/19040 | Augmentation | Providing Mechanical / Electrical Equipment for 11/0.433 KV Sub-station along with pumping station and disinfection arrangement Integrated Surface Water Based PWSS for Barasat-II Blocks in the District of North-24-Parganas. 1) Acceptance Order No. 211/MC-III dt. 01.03.2024 2) Administrative Approval No. 3497/PHE-28011/135/2023-SCHM CELL - of PHE Dept. dt. 17.11.2023 3) NIET No.-27/SEMCIII/WBPHED OF 2023-2024 (vide memo.no. 66/MC-III, Dated 13.01.2024) | Assistant Engineer | Junior Engineer | ORD/003082/2023-2024 | 757/EMD | 06/03/2024 | 01/04/2026 | B.T. PROJECTS PVT. LTD | 780 | 0 | 0 | 25
5 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | SURFACE BASED PWSS FOR BARASAT-II BLOCK | SM/19040 | Augmentation | Restoration of damaged UPVC pipeline and withdrawing relaying of DI/HDPE pipe distribution System including specials all complete and necessary road restoration work for the scheme of "Surface Based PWSS for Barasat-II Block in the district of North 24 Parganas under Barasat Arsenic Division, PHE Dte". | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000146/2024-2025 | 593/B.Ar.D. | 26/03/2025 | 22/09/2025 | SUPRITI ENTERPRISE | 380.56 | 0 | 0 | 20
6 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | SURFACE BASED PWSS FOR BARASAT-II BLOCK | SM/19040 | Augmentation | Wall writing on smooth wall surface (Preferably on Govt. premises / Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and two coat best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo picture etc. of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the blocks of Hasnabad (Part), Sandeshkhali-II (Part), Baduria (Part), Haroa, Rajarhat and Barasat-II (Part) all completed as per direction of EIC. (Rate inclusive 18% GST & 1% CESS) | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000084/2024-2025 | 53/B.Ar.D. | 08/01/2025 | 22/02/2025 | IMAGIN | 12.33 | 0 | 0 | 80
Total | [13 empty] | 7961.7 | 66.14 | 0.83