## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | SURFACE BASED PWSS FOR BARASAT-II BLOCK | SM/19040 | Augmentation | Survey, Design Drawing & DPR Preparation for Surface Based PWSS for Barasat-II Block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000241/2023-2024 | 539/B.Ar.D. | 13/03/2024 | 03/04/2024 | UMWELT ENGINEER PVT. LTD. | 66.14 | 66.14 | 100 | 100
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | SURFACE BASED PWSS FOR BARASAT-II BLOCK | SM/19040 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2023-2024 | 244/B.Ar.D. | 06/02/2024 | 06/02/2024 | Resource Division | 4012.31 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | SURFACE BASED PWSS FOR BARASAT-II BLOCK | SM/19040 | Augmentation | Laying, fitting, fixing, jointing etc of Primary & Secondary Rising Main and Construction of Ground Level Reservoir (GLR) Capacity 1100 CUM with all allied works of Barasat-II Block for Surface Based PWSS for Barasat-II Block in the district of North 24 Parganas under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000211/2023-2024 | 159/B.Ar.D. | 25/01/2024 | 24/01/2026 | SUPRITI ENTERPRISE | 2710.36 | 0 | 0 | 10
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | SURFACE BASED PWSS FOR BARASAT-II BLOCK | SM/19040 | Augmentation | Providing Mechanical / Electrical Equipment for 11/0.433 KV Sub-station along with pumping station and disinfection arrangement Integrated Surface Water Based PWSS for Barasat-II Blocks in the District of North-24-Parganas. 1) Acceptance Order No. 211/MC-III dt. 01.03.2024 2) Administrative Approval No. 3497/PHE-28011/135/2023-SCHM CELL - of PHE Dept. dt. 17.11.2023 3) NIET No.-27/SEMCIII/WBPHED OF 2023-2024 (vide memo.no. 66/MC-III, Dated 13.01.2024) | Assistant Engineer | Junior Engineer | ORD/003082/2023-2024 | 757/EMD | 06/03/2024 | 01/04/2026 | B.T. PROJECTS PVT. LTD | 780 | 0 | 0 | 25
5 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | SURFACE BASED PWSS FOR BARASAT-II BLOCK | SM/19040 | Augmentation | Restoration of damaged UPVC pipeline and withdrawing relaying of DI/HDPE pipe distribution System including specials all complete and necessary road restoration work for the scheme of "Surface Based PWSS for Barasat-II Block in the district of North 24 Parganas under Barasat Arsenic Division, PHE Dte". | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000146/2024-2025 | 593/B.Ar.D. | 26/03/2025 | 22/09/2025 | SUPRITI ENTERPRISE | 380.56 | 0 | 0 | 20
Total | [13 empty] | 7949.37 | 66.14 | 0.83