## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Resource | Annual Maintenance Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Mobile Laboratory Van related to WQMSP activity under Jal Jeevan Mission. | SM/07376 | Support-WQMSP | Name of Work: Annual Service Contract (ASC) for The Instruments & Equipments of 217 Water Testing Laboratories located In different blocks of West Bengal Under Public Health Department, Govt. of West Bengal. |  |  | ORD/000097/2020-2021 | 1556/RS | 28/12/2020 | 28/12/2021 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 294.56 | 171.83 | 58.33 | 0
2 | NORTH 24 PARGANAS |  | Resource | Annual Maintenance Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Mobile Laboratory Van related to WQMSP activity under Jal Jeevan Mission. | SM/07376 | Support-WQMSP | Name of Work: Annual Service Contract (ASC) for The Instruments & Equipments of 217 Water Testing Laboratories located In different blocks of West Bengal Under Public Health Department, Govt. of West Bengal. |  |  | ORD/000726/2021-2022 | 1290/RS | 29/12/2021 | 29/03/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 73.64 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Annual Maintenance Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Mobile Laboratory Van related to WQMSP activity under Jal Jeevan Mission. | SM/07376 | Support-WQMSP | Maintenance of Mobile Laboratory Van complete with internal fabrication, refrigeration, exhaust system, air conditioning system, waste disposal system and fully equipped with instruments, devices, consumables, reagents, accessories and safety gear for resource personnel for water quality testing in remote areas including external designing and painting for IEC propaganda complete with IEC audio visual aids as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. | Assistant Engineer, HQ-II, Barasat Arsenic Division |  | ORD/000186/2020-2021 | 549/B.Ar.D. | 26/02/2021 | 26/02/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 29.98 | 0 | 0 | 0
Total | [13 empty] | 398.18 | 171.83 | 43.15