## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Providing Functional Household Tap Connection(FHTC) within the Paschim Gobindapur, Nikash and Mathurabati Mouza of Borhal (Zone-I) PWSS | SM/06754 | Retrofitting | COLLECTION DATA FOR FHTC IN BORHAL |  |  | VCH/001324/2020-2021 |  | 08/12/2020 | 08/12/2020 | ARUN SEAL AND CO. | 2.15 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Providing Functional Household Tap Connection(FHTC) within the Paschim Gobindapur, Nikash and Mathurabati Mouza of Borhal (Zone-I) PWSS | SM/06754 | Retrofitting | Partial Modification & Extension of HDPE Water Distribution Line at Jangalsufi village of Borhal (Zone-I) & its adjoining mouzas Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Jangipara] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000245/2022-2023 | 448/Ser | 31/05/2022 | 15/06/2022 | ARUN SEAL AND CO. | 4.85 | 4.85 | 99.97 | 100
3 | HOOGHLY |  | Hooghly Division | Providing Functional Household Tap Connection(FHTC) within the Paschim Gobindapur, Nikash and Mathurabati Mouza of Borhal (Zone-I) PWSS | SM/06754 | Retrofitting | Providing 2200 nos F.H.T.C. in Akuti, Radhaballabhpur, Baidyagari, Paschim Durgapur, Budul Badul Hati, Bhandarhati, Ilampur, Gabtala, Dakshin Dilakash, Mandaran Dilakash, Khurigachhi, Kulakash, Kandar Panagar village of Borhal (Zone- II)and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Jangipara] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000100/2020-2021 | 1686/Hug | 17/12/2020 | 17/06/2021 | S & P CONSTRUCTION | 24.9 | 24.9 | 99.99 | 98
4 | HOOGHLY |  | Hooghly Division | Providing Functional Household Tap Connection(FHTC) within the Paschim Gobindapur, Nikash and Mathurabati Mouza of Borhal (Zone-I) PWSS | SM/06754 | Retrofitting | Estimate of Construction of Boundary Wall at 3rd T/W Site under BORHAL (Zone-II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/001291/2024-2025 | 63/SER | 20/01/2025 | 27/01/2025 | SURAJIT SINGHA RAY | 5 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Providing Functional Household Tap Connection(FHTC) within the Paschim Gobindapur, Nikash and Mathurabati Mouza of Borhal (Zone-I) PWSS | SM/06754 | Retrofitting | Estimate of Construction of Boundary Wall at 4th T/W Site under BORHAL (Zone-II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/001262/2024-2025 | 62/SER | 20/01/2025 | 27/01/2025 | SURAJIT SINGHA RAY | 5 | 0 | 0 | 0
Total | [13 empty] | 41.9 | 29.75 | 70.99