## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting Works of BAKSA PWSS for providing 1522 nos Functional Household Tap Connection(FHTC) | SM/06755 | Retrofitting | FHTC |  |  | VCH/002242/2020-2021 |  | 15/03/2021 | 15/03/2021 | MLG CONSTRUCTION | 35 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Retrofitting Works of BAKSA PWSS for providing 1522 nos Functional Household Tap Connection(FHTC) | SM/06755 | Retrofitting | Placement of Fund |  |  | VCH/002590/2021-2022 | 844368 | 19/01/2022 | 19/01/2022 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Retrofitting Works of BAKSA PWSS for providing 1522 nos Functional Household Tap Connection(FHTC) | SM/06755 | Retrofitting | Providing 800 nos Functional Household Tap Connection (FHTC) & extension of Laying Distribution System within the uncovered area of Baksa Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Chanditala-II] | Assistant Engineer (Civil) |  | ORD/000355/2020-2021 | 467/Hug | 26/02/2021 | 28/03/2021 | TAPAS ADHYA | 44.33 | 60.54 | 136.57 | 100
4 | HOOGHLY |  | Hooghly Division | Retrofitting Works of BAKSA PWSS for providing 1522 nos Functional Household Tap Connection(FHTC) | SM/06755 | Retrofitting | Providing 800 nos Functional Household Tap Connection (FHTC) & extension of Laying Distribution System within the uncovered area of Baksa Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Chanditala-II] | Assistant Engineer,Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000885/2020-2021 | 467/HUG | 26/02/2021 | 28/03/2021 | TAPAS ADHYA | 44.33 | 0 | 0 | 100
5 | HOOGHLY |  | Hooghly Division | Retrofitting Works of BAKSA PWSS for providing 1522 nos Functional Household Tap Connection(FHTC) | SM/06755 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000010/2022-2023 | 1122/7/HUG | 06/06/2022 | 06/06/2022 | Resource Division | 6.16 | 0 | 0 | 0
Total | [13 empty] | 141.35 | 60.54 | 42.83