## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting Works for Digsui-Heora PWSS(Zone-II ) for providing 1065 nos Functional Household Tap Connection(FHTC) | SM/06761 | Retrofitting | FHTC |  |  | VCH/000007/2021-2022 |  | 12/04/2021 | 12/04/2021 | M/S S.C CIVIL ENTERPRISE | 40.5 | 0 | 0 | 0
2 | HOOGHLY |  | Central Drilling | Retrofitting Works for Digsui-Heora PWSS(Zone-II ) for providing 1065 nos Functional Household Tap Connection(FHTC) | SM/06761 | Retrofitting | CONTINUATION FOR HIRING DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE DRILLER IN CHARGE, CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000096/2022-2023 | 361/CMSD-II (D) | 15/07/2022 | 14/08/2022 | ASHUTOSH PAL | 0.73 | 0.52 | 71.58 | 100
3 | HOOGHLY |  | Central Drilling | Retrofitting Works for Digsui-Heora PWSS(Zone-II ) for providing 1065 nos Functional Household Tap Connection(FHTC) | SM/06761 | Retrofitting | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR DIGSUI HEORA W/S SCHEME (Z-I), CHINSURAH MOGRA BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000025/2022-2023 | 296/CDD | 27/04/2022 | 27/05/2022 | C.M. ENTERPRISE | 11.21 | 6.2 | 55.32 | 100
4 | HOOGHLY |  | Hooghly Division | Retrofitting Works for Digsui-Heora PWSS(Zone-II ) for providing 1065 nos Functional Household Tap Connection(FHTC) | SM/06761 | Retrofitting | Providing 600 nos Functional Household Tap Connection (FHTC) within the command area of DIGSUI HOERA Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) |  | ORD/000359/2021-2022 | 120/Hug | 19/01/2022 | 18/02/2022 | DAS TRADING | 41.69 | 12.25 | 29.4 | 100
5 | HOOGHLY |  | Central Drilling | Retrofitting Works for Digsui-Heora PWSS(Zone-II ) for providing 1065 nos Functional Household Tap Connection(FHTC) | SM/06761 | Retrofitting | CONTINUATION FOR HIRING OF DEASEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE DRILLER IN CHARGE , CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000268/2022-2023 | 361/ CMSD-II | 15/07/2022 | 30/07/2022 | ASHUTOSH PAL | 0.73 | 0.29 | 39.87 | 100
6 | HOOGHLY |  | Central Drilling | Retrofitting Works for Digsui-Heora PWSS(Zone-II ) for providing 1065 nos Functional Household Tap Connection(FHTC) | SM/06761 | Retrofitting | Fuel charges for the month of November,22. car number - WB04H 6870. |  |  | BILL/00063/2022-2023 | BP-2022-23-300 | 06/01/2023 | 06/01/2023 | MIRA SERVICE STATION | 0.24 | 0 | 0 | 0
Total | [13 empty] | 95.09 | 19.26 | 20.26