## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Shitalpur & Pandugram Mouza of Arandi Water Supply Scheme | SM/06762 | Retrofitting | FHTC |  |  | VCH/001896/2020-2021 |  | 15/02/2021 | 15/02/2021 | M/S RAJKUMAR KHAN | 27 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Shitalpur & Pandugram Mouza of Arandi Water Supply Scheme | SM/06762 | Retrofitting | Providing 100 nos Functional Household Tap Connection (FHTC) within the command area of Arandi Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000271/2021-2022 | 425/HUG | 01/12/2021 | 31/12/2021 | M/S R K ENTERPRISE | 18.18 | 0 | 0 | 100
3 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Shitalpur & Pandugram Mouza of Arandi Water Supply Scheme | SM/06762 | Retrofitting | Providing 100 nos Functional Household Tap Connection (FHTC) within the command area of ARANDI Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000336/2021-2022 | 13/Hug | 04/01/2022 | 24/01/2022 | MS CHANDIMATA CONSTRUCTION | 13.37 | 0 | 0 | 100
Total | [13 empty] | 58.55 | 0 | 0