## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting Works for BAMANJOL PWSS for providing 1342 nos Functional Household Tap Connection(FHTC) | SM/06763 | Retrofitting | FHTC |  |  | VCH/000542/2021-2022 |  | 23/07/2021 | 23/07/2021 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 18.51 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Retrofitting Works for BAMANJOL PWSS for providing 1342 nos Functional Household Tap Connection(FHTC) | SM/06763 | Retrofitting | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of UPVC pipes & Strainer having depth upto180 Mtr at BAMONJOL PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. [2nd Call of WBPHE/EE/45/HUG/2022-23, Sl No-16] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000049/2023-2024 | 1201/HUG | 26/04/2023 | 26/05/2023 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 12.43 | 12.03 | 96.81 | 0
3 | HOOGHLY |  | Hooghly Division | Retrofitting Works for BAMANJOL PWSS for providing 1342 nos Functional Household Tap Connection(FHTC) | SM/06763 | Retrofitting | Providing F.H.T.C in leftout portion and Repairing of boundary wall at head work site and approach road at 3rd tubewell site of Bamanjol water supply scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000330/2024-2025 | 3717/HUG | 19/11/2024 | 01/08/2025 | SWARNA ENTERPRISE | 17.75 | 0 | 0 | 100
Total | [13 empty] | 48.69 | 12.03 | 24.71