## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Arandi & Mandaran Mouza of Arandi Water Supply Scheme | SM/06764 | Retrofitting | FHTC WORKS |  |  | VCH/001351/2020-2021 |  | 15/12/2020 | 15/12/2020 | TITAS CONSTRUCTION | 22.3 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Arandi & Mandaran Mouza of Arandi Water Supply Scheme | SM/06764 | Retrofitting | FHTC |  |  | VCH/000020/2021-2022 |  | 12/04/2021 | 12/04/2021 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 2.71 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Arandi & Mandaran Mouza of Arandi Water Supply Scheme | SM/06764 | Retrofitting | FHTC |  |  | VCH/001899/2020-2021 |  | 15/02/2021 | 15/02/2021 | TITAS CONSTRUCTION | 14.09 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Arandi & Mandaran Mouza of Arandi Water Supply Scheme | SM/06764 | Retrofitting | Placement of Fund |  |  | VCH/002590/2021-2022 | 844368 | 19/01/2022 | 19/01/2022 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Arandi & Mandaran Mouza of Arandi Water Supply Scheme | SM/06764 | Retrofitting | Providing 887 nos FHTC in Jaysinghachak & Pandugram village of Arandi PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000073/2020-2021 | 1539/Hug | 24/11/2020 | 24/05/2021 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 38.52 | 2.71 | 7.04 | 100
6 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Arandi & Mandaran Mouza of Arandi Water Supply Scheme | SM/06764 | Retrofitting | Providing 100 nos Functional Household Tap Connection (FHTC) within the command area of ARANDI Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000336/2021-2022 | 13/Hug | 04/01/2022 | 24/01/2022 | MS CHANDIMATA CONSTRUCTION | 13.37 | 0 | 0 | 100
Total | [13 empty] | 102.53 | 2.71 | 2.65