## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting Works for Borhal (Zone-I) PWSS for providing 1236 nos Functional Household Tap Connection(FHTC) | SM/06766 | Retrofitting | FHTC |  |  | VCH/000842/2021-2022 |  | 21/09/2021 | 21/09/2021 | M/S R.M. CONSTRUCTION | 16.1 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Retrofitting Works for Borhal (Zone-I) PWSS for providing 1236 nos Functional Household Tap Connection(FHTC) | SM/06766 | Retrofitting | FHTC |  |  | VCH/000846/2021-2022 |  | 21/09/2021 | 21/09/2021 | M/S RAJKUMAR KHAN | 9.49 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Retrofitting Works for Borhal (Zone-I) PWSS for providing 1236 nos Functional Household Tap Connection(FHTC) | SM/06766 | Retrofitting | FHTC |  |  | VCH/000185/2021-2022 |  | 24/05/2021 | 24/05/2021 | M/S RAJKUMAR KHAN | 11.84 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Retrofitting Works for Borhal (Zone-I) PWSS for providing 1236 nos Functional Household Tap Connection(FHTC) | SM/06766 | Retrofitting | FHTC BORHAL (Z-I) PWSS | Assistant Engineer (Civil) |  | ORD/000510/2021-2022 | 113/SECC | 19/11/2021 | 24/12/2021 | S & P ENTERPRISE | 53 | 0 | 0 | 100
5 | HOOGHLY |  | Hooghly Division | Retrofitting Works for Borhal (Zone-I) PWSS for providing 1236 nos Functional Household Tap Connection(FHTC) | SM/06766 | Retrofitting | FHTC |  |  | VCH/002098/2021-2022 |  | 28/01/2022 | 28/01/2022 | S & P ENTERPRISE | 55 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Retrofitting Works for Borhal (Zone-I) PWSS for providing 1236 nos Functional Household Tap Connection(FHTC) | SM/06766 | Retrofitting | Providing 2200 nos F.H.T.C. in Akuti, Radhaballabhpur, Baidyagari, Paschim Durgapur, Budul Badul Hati, Bhandarhati, Ilampur, Gabtala, Dakshin Dilakash, Mandaran Dilakash, Khurigachhi, Kulakash, Kandar Panagar village of Borhal (Zone- II)and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Jangipara] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000100/2020-2021 | 1686/Hug | 17/12/2020 | 17/06/2021 | S & P CONSTRUCTION | 24.9 | 0 | 0 | 98
7 | HOOGHLY |  | Hooghly Division | Retrofitting Works for Borhal (Zone-I) PWSS for providing 1236 nos Functional Household Tap Connection(FHTC) | SM/06766 | Retrofitting | Providing 28 nos F.H.T.C. including laying Pipe line in the left out portion of Borhal (Zone-I)and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Jangipara] | Assistant Engineer (Civil) |  | ORD/000284/2020-2021 | 331/Hug | 11/02/2021 | 13/03/2021 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 31.68 | 0 | 0 | 100
8 | HOOGHLY |  | Central Drilling | Retrofitting Works for Borhal (Zone-I) PWSS for providing 1236 nos Functional Household Tap Connection(FHTC) | SM/06766 | Retrofitting | SUPPLY & DELIVERY of pea size gravels at site for construction of tube well at BORHAL Z-II, hooghly district under CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000318/2022-2023 | 574/CMSD-I | 30/11/2022 | 07/12/2022 | C.M. ENTERPRISE | 0.98 | 0 | 0 | 100
Total | [13 empty] | 202.99 | 0 | 0