## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme | SM/06767 | Retrofitting | FHTC |  |  | VCH/001038/2021-2022 |  | 30/09/2021 | 30/09/2021 | M/S S.G. CONSTRUCTION | 13.22 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme | SM/06767 | Retrofitting | Placement of Fund |  |  | VCH/002590/2021-2022 | 844368 | 19/01/2022 | 19/01/2022 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme | SM/06767 | Retrofitting | Providing 512 nos F.H.T.C. in Krishnabati & Gazipur village of Malia and its Adjoining Mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. [Block-Haripal] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000083/2020-2021 | 1549/Hug | 24/11/2020 | 24/11/2021 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 18.11 | 3 | 16.56 | 100
4 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme | SM/06767 | Retrofitting | Providing 62 nos FHTC in Krishnabati village at Nawapara Habitation of Malia and its Adj. Mouzas Water Supply Scheme under Chandannagar Sub Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000423/2020-2021 | 59/Chan | 02/02/2021 | 18/02/2021 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 2.17 | 0.31 | 14.15 | 100
5 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme | SM/06767 | Retrofitting | PROVIDING 72 NOS FHTC FOR MALIA PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000457/2020-2021 | 88/CHAN | 15/02/2021 | 17/03/2021 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 3.16 | 0.41 | 12.89 | 100
6 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme | SM/06767 | Retrofitting | Providing 112 nos F.H.T.C. & extension of pipe line in left out portion of Dakshinkul, Baganbati& Hamir gachhi village of Malia and its Adjoining Mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. [Block-Haripal] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000880/2020-2021 | 327/HUG | 11/02/2021 | 13/03/2021 | M/S S.G. CONSTRUCTION | 10.08 | 10.08 | 100 | 100
7 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme | SM/06767 | Retrofitting | Providing F.H.T.C in leftout portion and repairing boundary wall of Malia water supply scheme under Chandannagar Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001246/2024-2025 | 3789/HUG | 25/11/2024 | 01/10/2025 | ROSE ENTERPRISE | 11.75 | 0 | 0 | 100
8 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme | SM/06767 | Retrofitting | Cleaning Choked pipeline and laying additional pipeline at Gazipur Village of Malia Piped Water Supply Scheme under Chandanagar Sub -Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000280/2024-2025 | 933/Chan | 05/11/2024 | 20/11/2024 | SHREE JAGANNATH ENTERPRISE | 0.98 | 0 | 0 | 100
9 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme | SM/06767 | Retrofitting | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MALIA PWSS of Chandannagar Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002423/2024-2025 | 225/Chan | 20/02/2025 | 12/03/2025 | AMBIAN INFRASTRUCTURE (PARTNERSHIP) | 0.98 | 0.98 | 100 | 100
Total | [13 empty] | 71.98 | 14.77 | 20.52