## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Akuti, Radhaballabhpur, Baidyagari, Paschim Durgapur,Budul Badul Hati,Bhandarhati,Ilampur, Gabtala,Dakshin Dilakash Mouza of Borhol Zone-II Water Supply Scheme | SM/06987 | Retrofitting | Providing 375 nos Functional Household Tap Connection (FHTC) within the command area of BORHAL(ZONE-I) Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000361/2021-2022 | 122/Hug | 19/01/2022 | 13/02/2022 | K. JAGADHATRY & CO. | 15.98 | 15.98 | 99.98 | 100
2 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Akuti, Radhaballabhpur, Baidyagari, Paschim Durgapur,Budul Badul Hati,Bhandarhati,Ilampur, Gabtala,Dakshin Dilakash Mouza of Borhol Zone-II Water Supply Scheme | SM/06987 | Retrofitting | Providing 250 nos F.H.T.C. in Kotalpur village of Patna Bhairabpur and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | Assistant Engineer (Civil) |  | ORD/000268/2020-2021 | 262/Hug | 03/02/2021 | 23/02/2021 | K JAGADHATRY & CO | 13.62 | 8.38 | 61.56 | 0
3 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Akuti, Radhaballabhpur, Baidyagari, Paschim Durgapur,Budul Badul Hati,Bhandarhati,Ilampur, Gabtala,Dakshin Dilakash Mouza of Borhol Zone-II Water Supply Scheme | SM/06987 | Retrofitting | Providing 28 nos F.H.T.C. including laying Pipe line in the left out portion of Borhal (Zone-I)and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Jangipara] | Assistant Engineer (Civil) |  | ORD/000284/2020-2021 | 331/Hug | 11/02/2021 | 13/03/2021 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 31.68 | 16.31 | 51.49 | 100
4 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Akuti, Radhaballabhpur, Baidyagari, Paschim Durgapur,Budul Badul Hati,Bhandarhati,Ilampur, Gabtala,Dakshin Dilakash Mouza of Borhol Zone-II Water Supply Scheme | SM/06987 | Retrofitting | Providing 2200 nos F.H.T.C. in Akuti, Radhaballabhpur, Baidyagari, Paschim Durgapur, Budul Badul Hati, Bhandarhati, Ilampur, Gabtala, Dakshin Dilakash, Mandaran Dilakash, Khurigachhi, Kulakash, Kandar Panagar village of Borhal (Zone- II)and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Jangipara] | Assistant Engineer (Civil) |  | ORD/000881/2020-2021 | 1686/Hug. | 17/12/2020 | 26/01/2021 | S & P ENTERPRISE | 103.59 | 17.89 | 17.27 | 98
Total | [13 empty] | 164.87 | 58.57 | 35.52