## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Harishchak (Left bank of Sundeswari river) Water Supply Scheme | SM/06989 | Retrofitting | FHTC |  |  | VCH/001894/2020-2021 |  | 15/02/2021 | 15/02/2021 | P.B. ENTERPRISE (PINTU BHADURI) | 77 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Harishchak (Left bank of Sundeswari river) Water Supply Scheme | SM/06989 | Retrofitting | Providing 114 nos FHTC for different mouzas under Harishchak PWSS under Hooghly Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000501/2021-2022 | 524/ARG | 30/11/2021 | 14/01/2022 | MAA JAGADHATRI CONSTRUCTION | 4.74 | 4.74 | 100 | 0
3 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Harishchak (Left bank of Sundeswari river) Water Supply Scheme | SM/06989 | Retrofitting | Providing 450 nos Functional Household Tap Connection (FHTC) within the command area of Harischak Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000247/2021-2022 | 1998/Hug | 12/11/2021 | 12/12/2021 | M/S SHIVAM UDYOG | 20.68 | 15.86 | 76.71 | 0
Total | [13 empty] | 102.41 | 20.6 | 20.11