## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SRIPUR Water Supply Scheme | SM/06991 | Retrofitting | FHTC |  |  | VCH/002284/2020-2021 |  | 15/03/2021 | 15/03/2021 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 10 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SRIPUR Water Supply Scheme | SM/06991 | Retrofitting | FHTC |  |  | VCH/002106/2021-2022 |  | 28/01/2022 | 28/01/2022 | MALLIKA ENTERPRISE | 29 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SRIPUR Water Supply Scheme | SM/06991 | Retrofitting | FHTC |  |  | VCH/002096/2021-2022 |  | 28/01/2022 | 28/01/2022 | MALLIKA ENTERPRISE | 9.92 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SRIPUR Water Supply Scheme | SM/06991 | Retrofitting | Providing 1000 nos Functional Household Tap Connection (FHTC) within the command area of Sripur Balagar Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000292/2021-2022 | 2203/Hug | 14/12/2021 | 12/02/2022 | MALLIKA ENTERPRISE | 46.52 | 26.77 | 57.54 | 0
5 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SRIPUR Water Supply Scheme | SM/06991 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000126/2021-2022 | 2195/HUG | 14/12/2021 | 14/12/2021 | Resource Division | 1.59 | 0 | 0 | 0
Total | [13 empty] | 97.03 | 26.77 | 27.59