## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jangalpara Water Supply Scheme | SM/06992 | Retrofitting | FHTC |  |  | VCH/000843/2021-2022 |  | 21/09/2021 | 21/09/2021 | RAJ CONSTRUCTION | 43.8 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jangalpara Water Supply Scheme | SM/06992 | Retrofitting | Providing 47 nos. Functional Household Tap Connection (FHTC) in AWG Centers (the command area of Jangalpara, Jangipara & Rajbalhat Water Supply Scheme) under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000314/2021-2022 | 220/SER | 20/12/2021 | 14/01/2022 | M/S SAYAN CHAKRABORTY | 1.95 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jangalpara Water Supply Scheme | SM/06992 | Retrofitting | Providing 1487 nos F.H.T.C. in Jangalpara Village of Jangalpara and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Chanditala-I] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000467/2020-2021 | 473/Hug | 26/02/2021 | 07/04/2021 | RAJ CONSTRUCTION | 51.8 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jangalpara Water Supply Scheme | SM/06992 | Retrofitting | Survey of FHTC Work under Rajyadharpur, Rishra, Nabagram GP KMDA Water Supply areas and Jangalpara, Krishnarampur, Chanditala, Panchghora, Begampur & Mollarber Water Supply areas under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000388/2021-2022 | 294/SER | 21/02/2022 | 07/04/2022 | BAKSHI ENTERPRISE | 2.99 | 0 | 0 | 0
5 | HOOGHLY |  | Central Drilling | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jangalpara Water Supply Scheme | SM/06992 | Retrofitting | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR JANGALPARA W/S SCHEME, CHANDITALA-I BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000387/2022-2023 | 2000/CDD | 08/02/2023 | 10/03/2023 | CHANDA ENTERPRISE | 12.54 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jangalpara Water Supply Scheme | SM/06992 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000122/2021-2022 | 2198/1/HUG | 14/12/2021 | 14/12/2021 | Resource Division | 1.59 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jangalpara Water Supply Scheme | SM/06992 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000004/2022-2023 | 1122/1/HUG | 06/06/2022 | 06/06/2022 | Resource Division | 12.32 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jangalpara Water Supply Scheme | SM/06992 | Retrofitting | Providing 1487 nos F.H.T.C. in Jangalpara Village of Jangalpara and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Chanditala] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000894/2020-2021 | 473/HUG | 26/02/2021 | 07/04/2021 | RAJ CONSTRUCTION | 69.87 | 0 | 0 | 72
Total | [13 empty] | 196.86 | 0 | 0