## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Mandaran Water Supply Scheme | SM/06993 | Retrofitting | FHTC |  |  | VCH/000591/2021-2022 |  | 17/08/2021 | 17/08/2021 | MAA TARA CONSTRUCTION | 12.88 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Mandaran Water Supply Scheme | SM/06993 | Retrofitting | .... |  |  | VCH/000827/2021-2022 | 844334 | 19/08/2021 | 19/08/2021 | MOUMITA SINGHA BHATTACHATYA | 0.48 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Mandaran Water Supply Scheme | SM/06993 | Retrofitting | Placement of Fund |  |  | VCH/002590/2021-2022 | 844368 | 19/01/2022 | 19/01/2022 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Mandaran Water Supply Scheme | SM/06993 | Retrofitting | Providing 823 nos F.H.T.C. in the Rudrashanda,Mandaran & Sankpur village of Mandaran and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Pandua] | Assistant Engineer (Civil) |  | ORD/000104/2020-2021 | 1691/Hug | 17/12/2020 | 17/06/2021 | MAA TARA CONSTRUCTION | 38.75 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Mandaran Water Supply Scheme | SM/06993 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000094/2021-2022 | 2097/34/Hug | 26/11/2021 | 26/11/2021 | Resource Division | 0.83 | 0 | 0 | 0
Total | [13 empty] | 64.47 | 0 | 0