## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jaykrishnapur (Purba Amarpur,Jaykrishnapur mouza) Water Supply Scheme under | SM/07150 | Retrofitting | Providing 220 nos FHTC Mathura village of Joukrishnapur and its Adj. Mouzas PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000755/2020-2021 | 1440/Hug. | 02/02/2021 | 19/03/2021 | R AND D TRADERS | 10.01 | 10.01 | 100 | 0
2 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jaykrishnapur (Purba Amarpur,Jaykrishnapur mouza) Water Supply Scheme under | SM/07150 | Retrofitting | Providing 220 nos F.H.T.C. in Mathura village of Jaykrishnapur and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I] | Assistant Engineer | Junior Engineer (Civill) | ORD/000244/2020-2021 | 243/Hug | 02/02/2021 | 22/02/2021 | R AND D TRADERS | 10.05 | 0 | 0 | 0
Total | [13 empty] | 20.06 | 10.01 | 49.91