## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur(Within Munshi Para, Patra Para,Pramanik Para, Roy Para- Danga, Sabalsinghapur, Dolui Para, Sanki Para, Santra Para, Santra Para-North,Seik | SM/07151 | Retrofitting | FHTC |  |  | VCH/000027/2021-2022 |  | 12/04/2021 | 12/04/2021 | TITAS CONSTRUCTION | 8.56 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur(Within Munshi Para, Patra Para,Pramanik Para, Roy Para- Danga, Sabalsinghapur, Dolui Para, Sanki Para, Santra Para, Santra Para-North,Seik | SM/07151 | Retrofitting | FHTC |  |  | VCH/000541/2021-2022 |  | 23/07/2021 | 23/07/2021 | TITAS CONSTRUCTION | 12.14 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur(Within Munshi Para, Patra Para,Pramanik Para, Roy Para- Danga, Sabalsinghapur, Dolui Para, Sanki Para, Santra Para, Santra Para-North,Seik | SM/07151 | Retrofitting | Providing 650 nos Functional Household Tap Connection (FHTC) within the command area of SABALSINGHAPUR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000342/2021-2022 | 19/Hug | 04/01/2022 | 05/03/2022 | M/S R.K. CHOUDHURI | 26.47 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur(Within Munshi Para, Patra Para,Pramanik Para, Roy Para- Danga, Sabalsinghapur, Dolui Para, Sanki Para, Santra Para, Santra Para-North,Seik | SM/07151 | Retrofitting | Providing 575 nos Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000246/2021-2022 | 1997/Hug | 12/11/2021 | 22/12/2021 | STP ENTERPRISE | 31.38 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur(Within Munshi Para, Patra Para,Pramanik Para, Roy Para- Danga, Sabalsinghapur, Dolui Para, Sanki Para, Santra Para, Santra Para-North,Seik | SM/07151 | Retrofitting | Providing 114 nos. Functional Household Tap Connection (F.H.T.C) within Command area of Munshipara Habitation of Sabalsinghapur Village under Sabalsinghapur Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte. [Block-Khanakul-II] | Assistant Engineer | Junior Engineer (Civill) | ORD/000347/2021-2022 | 527/Arg | 30/11/2021 | 30/12/2021 | P.K. GHOSH & CO. | 4.7 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur(Within Munshi Para, Patra Para,Pramanik Para, Roy Para- Danga, Sabalsinghapur, Dolui Para, Sanki Para, Santra Para, Santra Para-North,Seik | SM/07151 | Retrofitting | Providing 114 nos. Functional Household Tap Connection (F.H.T.C) within Command area of Munshipara Habitation of Sabalsinghapur Village under Sabalsinghapur Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte. [Block-Khanakul-II] | Assistant Engineer | Junior Engineer (Civill) | ORD/000540/2021-2022 | 527/ARG | 15/02/2022 | 17/03/2022 | P.K. GHOSH & CO. | 4.79 | 0 | 0 | 0
Total | [13 empty] | 88.04 | 0 | 0