## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. | SM/07436 | Retrofitting | FHTC |  |  | VCH/000857/2021-2022 |  | 21/09/2021 | 21/09/2021 | M/S S.G. CONSTRUCTION | 23.77 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. | SM/07436 | Retrofitting | FHTC |  |  | VCH/000853/2021-2022 |  | 21/09/2021 | 21/09/2021 | MS PRADIP KUMAR PAL | 14.04 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. | SM/07436 | Retrofitting | FHTC |  |  | VCH/000537/2021-2022 |  | 23/07/2021 | 23/07/2021 | M/S S.G. CONSTRUCTION | 23.14 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. | SM/07436 | Retrofitting | FHTC |  |  | VCH/000517/2021-2022 |  | 23/07/2021 | 23/07/2021 | MS PRADIP KUMAR PAL | 10.4 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. | SM/07436 | Retrofitting | Providing 400 nos Functional Household Tap Connection (FHTC) within the command area of Kulihanda & AMODGHATA Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000355/2021-2022 | 116/Hug | 19/01/2022 | 08/02/2022 | R.K. TRADERS | 25.16 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. | SM/07436 | Retrofitting | Construction of 3.65 m X 3.60 m Switch Room with Sanitary & Water Supply & Sanitation Arrangement at 4th T/W Site of Kulihanda W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000117/2022-2023 | 399/CH | 06/05/2022 | 10/06/2022 | SADHUKHAN ENTERPRISE | 4.99 | 0 | 0 | 0
7 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. | SM/07436 | Retrofitting | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KULIHANDA PWSS, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000146/2022-2023 | 135/S&WSD | 12/08/2022 | 27/08/2022 | ASHUTOSH DAS & CO | 5 | 0 | 0 | 0
8 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. | SM/07436 | Retrofitting | SUPPLY & DELIVERY OF CONSUMABLES AND OTHERS WORKS AT SITE FOR construction of tube well at kulihanda pwss, polba dadpur block, hooghly district under cdd, phe dte. |  |  | ORD/000148/2022-2023 | 136/S&WSD | 12/08/2022 | 27/08/2022 | ASHUTOSH DAS & CO | 4.99 | 0 | 0 | 0
9 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. | SM/07436 | Retrofitting | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT KULIHANDA PWSS, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000147/2022-2023 | 134/S&WSD | 12/08/2022 | 27/08/2022 | ASHUTOSH DAS & CO | 3.92 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. | SM/07436 | Retrofitting | Providing 800 nos Functional Household Tap Connection (FHTC) within the command area of Kulihanda Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000208/2021-2022 | 1677/hug | 13/09/2021 | 13/10/2021 | EVEREST CONSULTANT SERVICES | 35.63 | 0 | 0 | 0
11 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. | SM/07436 | Retrofitting | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 210 mtrs. Depth) by utilising Departmental machineries for baidyapur W/S Scheme, Tarakeswar block under hooghly District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000433/2022-2023 | 1724/CDD | 29/12/2022 | 28/01/2023 | DEY ENTERPRISE | 13.83 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. | SM/07436 | Retrofitting | Connection of 4th T.W. with existing distribution pipe line at Kulihanda W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000517/2023-2024 | 824/CH | 31/08/2023 | 15/09/2023 | M/S BIMAL DAS AND CO. | 0.96 | 0 | 0 | 80
13 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. | SM/07436 | Retrofitting | Sinking of 2 (Two) No Big dia tube well (250 mm X 150 mm) with supply of PVC Pipe and strainer and having depth upto 180 M at 3rd TW site of Kulihanda W/S Scheme under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000893/2023-2024 | 817/HUG | 11/03/2024 | 10/04/2024 | M/S. R. M. CONSTRUCTION | 19.52 | 0 | 0 | 100
14 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. | SM/07436 | Retrofitting | Providing FHTC at the left out portions of Different area for providing FHTC in Kulihanda Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000837/2023-2024 | 215/CH | 29/02/2024 | 07/03/2024 | MAA BUNAMATA ENTERPRISE | 0.98 | 0 | 0 | 45
15 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. | SM/07436 | Retrofitting | Laying of HDPE Pipeline for providing FHTC at the left out portions of at Kulihanda Piped Water Supply Scheme under Chinsurah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000838/2023-2024 | 216/CH | 29/02/2024 | 07/03/2024 | MAA BUNAMATA ENTERPRISE | 0.98 | 0 | 0 | 45
16 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. | SM/07436 | Retrofitting | Providing 1969 nos F.H.T.C. in Kulihanda (CT) Village of Kulihanda and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Chinsurah Mogra] |  |  | ORD/000951/2022-2023 | 457CH | 01/10/2022 | 20/11/2022 | MLG CONSTRUCTION | 102.5 | 0 | 0 | 0
Total | [13 empty] | 289.81 | 0 | 0