## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NAMAJGRAM WATER SUPPLY SCHEME. | SM/07440 | Retrofitting | FHTC |  |  | VCH/001125/2021-2022 |  | 16/11/2021 | 16/11/2021 | GHOSH CONCERN | 24.1 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NAMAJGRAM WATER SUPPLY SCHEME. | SM/07440 | Retrofitting | FHTC |  |  | VCH/000935/2021-2022 |  | 24/09/2021 | 24/09/2021 | M/S T.K.B. CONSTRUCTION | 7.71 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NAMAJGRAM WATER SUPPLY SCHEME. | SM/07440 | Retrofitting | FHTC |  |  | VCH/000014/2021-2022 |  | 12/04/2021 | 12/04/2021 | M/S T.K.B. CONSTRUCTION | 6.96 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NAMAJGRAM WATER SUPPLY SCHEME. | SM/07440 | Retrofitting | FHTC |  |  | VCH/001028/2021-2022 |  | 30/09/2021 | 30/09/2021 | SAMRAT CONSTRUCTION | 19.34 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NAMAJGRAM WATER SUPPLY SCHEME. | SM/07440 | Retrofitting | Providing 220 nos Functional Household Tap Connection (FHTC) within the command area of Namajgram & SUDARSHAN Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000356/2021-2022 | 117/Hug | 19/01/2022 | 03/02/2022 | TOTON MONDAL | 18.26 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NAMAJGRAM WATER SUPPLY SCHEME. | SM/07440 | Retrofitting | Providing 717 nos F.H.T.C. in Marsit&Kshirkundi Village of Namajgram and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Pandua] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000328/2020-2021 | 400/Hug | 15/02/2021 | 17/03/2021 | GHOSH CONCERN | 37.28 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NAMAJGRAM WATER SUPPLY SCHEME. | SM/07440 | Retrofitting | Providing 934 nos F.H.T.C. in Kulipukur & Matukpur Village of Namajgram and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Pandua] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000021/2021-2022 | 959/Hug | 10/05/2021 | 09/06/2021 | SAMRAT CONSTRUCTION | 48.63 | 0 | 0 | 80
Total | [13 empty] | 162.27 | 0 | 0