## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AMRA WATER SUPPLY SCHEME. | SM/07442 | Retrofitting | FHTC |  |  | VCH/000523/2021-2022 |  | 23/07/2021 | 23/07/2021 | DIPTI TRADERS | 30.58 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AMRA WATER SUPPLY SCHEME. | SM/07442 | Retrofitting | FHTC |  |  | VCH/002543/2020-2021 |  | 19/03/2021 | 19/03/2021 | DIPTI TRADERS | 30 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AMRA WATER SUPPLY SCHEME. | SM/07442 | Retrofitting | FHTC |  |  | VCH/002285/2020-2021 |  | 15/03/2021 | 15/03/2021 | DIPTI TRADERS | 30 | 0 | 0 | 0
4 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AMRA WATER SUPPLY SCHEME. | SM/07442 | Retrofitting | PROVIDING DRILLING CREWS AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR AMRA W/S SCHEME, POLBADADPUR BLOCK UNDER HOOGHLY DISTRICT , CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000011/2022-2023 | 294/CDD | 27/04/2022 | 27/05/2022 | C.M. ENTERPRISE | 11.21 | 0 | 0 | 0
5 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AMRA WATER SUPPLY SCHEME. | SM/07442 | Retrofitting | PROVIDING DRILLING CREWS AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR AMRA W/S SCHEME (HEAD WORKS), POLBA DADPUR BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000008/2022-2023 | 302/CDD | 27/04/2022 | 27/05/2022 | C.M. ENTERPRISE | 11.21 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AMRA WATER SUPPLY SCHEME. | SM/07442 | Retrofitting | Placement of Fund |  |  | VCH/002590/2021-2022 | 844368 | 19/01/2022 | 19/01/2022 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0 | 0
7 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AMRA WATER SUPPLY SCHEME. | SM/07442 | Retrofitting | ROUTINE MAINTENANCE OF COMPRESSOR AND REPAIRING OF OTHERS ATTACHED WITH RIG MACHINE NO. KORES/DR/1000 UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000242/2021-2022 | 635/CMSD-II (D) | 23/12/2021 | 07/01/2022 | M/S B.P.TRADING CORPORATION | 3.37 | 0 | 0 | 0
8 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AMRA WATER SUPPLY SCHEME. | SM/07442 | Retrofitting | REPAIRING OF MUD PUMP FLUID CHAMBER, TRANSMISSION LINE AND OTHERS WORKS ALONG WITH SUPPLY OF DRILLING ACCESSORYU OF RIG MACHINE- JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000273/2021-2022 | 72/CMSD-I | 30/03/2022 | 14/04/2022 | PADMA ENGINEERING & CO. | 4 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AMRA WATER SUPPLY SCHEME. | SM/07442 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000127/2021-2022 | 2195/1/HUG | 14/12/2021 | 14/12/2021 | Resource Division | 1.59 | 0 | 0 | 0
Total | [13 empty] | 133.5 | 0 | 0