## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHAPTA WATER SUPPLY SCHEME. | SM/07443 | Retrofitting | FHTC |  |  | VCH/000190/2021-2022 |  | 24/05/2021 | 24/05/2021 | DAS ENTERPRISE (SAMIR DAS) | 23.32 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHAPTA WATER SUPPLY SCHEME. | SM/07443 | Retrofitting | FHTC |  |  | VCH/000535/2021-2022 |  | 23/07/2021 | 23/07/2021 | BIMAL KUMAR HALDER | 9.98 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHAPTA WATER SUPPLY SCHEME. | SM/07443 | Retrofitting | FHTC |  |  | VCH/000603/2021-2022 |  | 17/08/2021 | 17/08/2021 | DAS ENTERPRISE (SAMIR DAS) | 14.73 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHAPTA WATER SUPPLY SCHEME. | SM/07443 | Retrofitting | FHTC |  |  | VCH/002613/2020-2021 |  | 19/03/2021 | 19/03/2021 | DAS ENTERPRISE (SAMIR DAS) | 10.96 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHAPTA WATER SUPPLY SCHEME. | SM/07443 | Retrofitting | FHTC |  |  | VCH/001923/2020-2021 |  | 15/02/2021 | 15/02/2021 | TOTON MONDAL | 16 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHAPTA WATER SUPPLY SCHEME. | SM/07443 | Retrofitting | FHTC |  |  | VCH/000847/2021-2022 |  | 21/09/2021 | 21/09/2021 | TOTON MONDAL | 7.25 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHAPTA WATER SUPPLY SCHEME. | SM/07443 | Retrofitting | FHTC |  |  | VCH/001095/2021-2022 |  | 06/10/2021 | 06/10/2021 | DAS ENTERPRISE (SAMIR DAS) | 6.67 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHAPTA WATER SUPPLY SCHEME. | SM/07443 | Retrofitting | FHTC |  |  | VCH/000514/2021-2022 |  | 23/07/2021 | 23/07/2021 | BIMAL KUMAR HALDER | 9.98 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHAPTA WATER SUPPLY SCHEME. | SM/07443 | Retrofitting | ... |  |  | VCH/002577/2021-2022 | 844375 | 17/12/2021 | 17/12/2021 | MOUMITA SINGHA BHATTACHATYA | 0.31 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHAPTA WATER SUPPLY SCHEME. | SM/07443 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000170/2021-2022 | 428/5-5/Hug | 07/03/2022 | 07/03/2022 | Resource Division | 11 | 0 | 0 | 0
Total | [13 empty] | 110.18 | 0 | 0