## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PANCHGHORA Water Supply Scheme | SM/07462 | Retrofitting | Providing 50 nos. Functional Household Tap Connection (FHTC) to the Educational Institutions within the command area of various Water Supply Schemes (Retrofitting Schemes- Baksa, Chikrand, Panchghora & Augmentation Schemes- Chanditala, Janai, Begampur, Kharsarai, Purba Tajpur) under Serampore Sub-Division of Hooghly Division P.H.E. Dte. [Chanditala-II] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000315/2021-2022 | 219/SER | 20/12/2021 | 14/01/2022 | M/S SHIVAM UDYOG | 2.08 | 2.08 | 100 | 0
2 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PANCHGHORA Water Supply Scheme | SM/07462 | Retrofitting | Providing 100 nos Functional Household Tap Connection (FHTC) within the command area of Panchghora Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000319/2021-2022 | 2308/Hug | 24/12/2021 | 13/01/2022 | M/S S.G. CONSTRUCTION | 7.01 | 6.9 | 98.53 | 0
3 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PANCHGHORA Water Supply Scheme | SM/07462 | Retrofitting | Survey of FHTC Work under Rajyadharpur, Rishra, Nabagram GP KMDA Water Supply areas and Jangalpara, Krishnarampur, Chanditala, Panchghora, Begampur & Mollarber Water Supply areas under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000388/2021-2022 | 294/SER | 21/02/2022 | 07/04/2022 | BAKSHI ENTERPRISE | 2.99 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PANCHGHORA Water Supply Scheme | SM/07462 | Retrofitting | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at PANCHGHORA PWSS of SERAMPORE Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000786/2022-2023 | 879/HUG | 27/03/2023 | 26/04/2023 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 11.32 | 11.32 | 100 | 0
5 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PANCHGHORA Water Supply Scheme | SM/07462 | Retrofitting | Repairing of Damaged Road due to FHTC Works at different mouzas (Joykrishnapur) of Panchghora W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) |  | ORD/000340/2024-2025 | 638/SER | 05/11/2024 | 12/11/2024 | MS CHANDIMATA CONSTRUCTION | 4.82 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PANCHGHORA Water Supply Scheme | SM/07462 | Retrofitting | Sinking of Additional 300 X 200 mm dia Tubewell 180 mtr depth, Construction of Switch Room, Boundary wall and rising main with interconnection at Panchghora W/S Scheme, Chanditala-II Block under Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000746/2023-2024 | 378/HUG | 08/02/2024 | 08/05/2024 | GHOSH ENTERPRISE (SOUMEN GHOSH) | 35.41 | 29.9 | 84.43 | 80
7 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PANCHGHORA Water Supply Scheme | SM/07462 | Retrofitting | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Panchghora PWSS 2. Chanditala PWSS 3. Madhabpur PWSS 4. Jagannathbati PWSS 5. Purbatajpur PWSS 6. Jangipara PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000942/2023-2024 | 112/SER | 23/02/2024 | 01/03/2024 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100 | 80
8 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PANCHGHORA Water Supply Scheme | SM/07462 | Retrofitting | Laying Rising Main and Protection work at Panchghora Jolapara of Panchghora W/s Scheme Chanditala-II Block under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001563/2024-2025 | 327/HUG | 05/02/2025 | 23/01/2026 | BIMAL KUMAR HALDER | 31.5 | 0 | 0 | 35
9 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PANCHGHORA Water Supply Scheme | SM/07462 | Retrofitting | Laying of C.I/D.I pipes & specials for connection of T.W No.-III with distribution system at 3rd TW Site and Laying HDPE pipe for extension of LDS with FHTC & Construction of 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply & Sanitation arrangement of Panchghara W/S Scheme under Serampore Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000004/2023-2024 | 998/HUG | 05/04/2023 | 01/04/2025 | MS CHANDIMATA CONSTRUCTION | 77.55 | 41.06 | 52.94 | 50
Total | [13 empty] | 173.63 | 92.21 | 53.11