## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of DHIBAGNAN Water Supply Scheme | SM/07463 | Retrofitting | FHTC |  |  | VCH/000013/2021-2022 |  | 12/04/2021 | 12/04/2021 | M/S PRADYUT KUMAR HAZRA | 75.95 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of DHIBAGNAN Water Supply Scheme | SM/07463 | Retrofitting | FHTC |  |  | VCH/002583/2020-2021 |  | 19/03/2021 | 19/03/2021 | M/S PRADYUT KUMAR HAZRA | 65 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of DHIBAGNAN Water Supply Scheme | SM/07463 | Retrofitting | Providing 770 nos Functional Household Tap Connection (FHTC) within the command area of DIHIBAGNAN Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. Work Allotted : 385 Nos FHTC out of 770 Nos FHTC within the command area of DIHIBAGNAN Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Estimate Value : Rs. 1599635.50 (50% of Rs. 3199271.00) | Assistant Engineer | Junior Engineer (Civill) | ORD/000311/2021-2022 | 2230/Hug | 15/12/2021 | 14/01/2022 | M/S T.K.B. CONSTRUCTION | 25.6 | 9.48 | 37.03 | 0
4 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of DHIBAGNAN Water Supply Scheme | SM/07463 | Retrofitting | Providing 100 nos Functional Household Tap Connection (FHTC) within Dihibagnan, Para Bagnan & Bhabanipur Village of Dihibagnan Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte.[Block-Arambagh] | Assistant Engineer | Junior Engineer (Civill) | ORD/000012/2022-2023 | 713/Hug | 07/04/2022 | 02/05/2022 | BAKSHI ENTERPRISE | 11 | 6.39 | 58.09 | 0
5 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of DHIBAGNAN Water Supply Scheme | SM/07463 | Retrofitting | Providing 840 nos Functional Household Tap Connection (FHTC) within the command area of Dihibagnan Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000230/2021-2022 | 1915/Hug | 27/10/2021 | 06/12/2021 | M/S PRADYUT KUMAR HAZRA | 40.43 | 35.11 | 86.83 | 0
6 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of DHIBAGNAN Water Supply Scheme | SM/07463 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000124/2021-2022 | 2196/HUG | 14/12/2021 | 14/12/2021 | Resource Division | 1.59 | 0 | 0 | 0
Total | [13 empty] | 219.57 | 50.98 | 23.22